## Submittal Listing
Fort Wayne - Standard Submittal Listing |  |  |  |  | Version Control: 4/7/2026
Section Number | Section Name | Submittal Number | Multiple Submittals (Add as Needed) | Document Type | Submittal Title | Description | Submittal Category | Workflow
Division 01 - General Requirements
01 29 73 | Schedule of Values | 1.5.B.9.a |  | Schedule of Values - Informational | Schedule of Values | Schedule of values including appropriate breakdown of materials intended to be installed | Preconstruction
01 31 19.13 | Pre-Construction Meetings | 1.5.B.9.a |  | Special Procedures - Informational | Emergency Contacts | listing of emergency contacts, include contact names, numbers. Resubmit if contacts change throughout the duration of the project | Preconstruction
01 31 19.13 | Pre-Construction Meetings | 1.5.B.9.b |  | Special Procedures - Informational | Subcontractor List | listing of proposed subcontractors and contact information | Preconstruction
01 31 19.13 | Pre-Construction Meetings | 1.5.B.9.c |  | Special Procedures - Informational | Preliminary Schedule of Submittals | preliminary schedule of submittals including submittal titles, including appropriate breakdown of Work | Preconstruction
01 31 19.13 | Pre-Construction Meetings | 1.5B.9.d |  | Special Procedures - Informational | Preliminary Schedule of Values | preliminary schedule of values including, appropriate breakdown of Work | Preconstruction
01 32 16 | Construction Progress Schedule | 1.5.B.9.a |  | Special Procedures - Informational | Preliminary Progress Schedule | Horizontal bar or Gantt chart | Preconstruction
01 32 16 | Construction Progress Schedule | 1.5.B.9.b | 1.5.B.9.b.1. | Special Procedures - Informational | Monthly Progress Schedule | Horizontal bar or Gantt chart - Include listing of activities since previous schedule submittal. And discussion of problems . | Construction
01 32 16 | Construction Progress Schedule | 1.5.B.9.c |  | Special Procedures - Informational | Recovery Schedule | Horizontal bar or Gantt chart - Submit as required when work is 14 or more days behind Progress Schedule | Preconstruction
01 35 63.01 | Sustainability Requirements | 1.5.B.8.a |  | Sustainable Design - Informational | Sustainability Plan | Plan outlining method for how Contractor plans to meet targets stipulated in Table 1 Envision Credits for the project. | Preconstruction
01 35 63.01 | Sustainability Requirements | 1.5.B.8.b |  | Sustainable Design - Informational | LD 1.1 Provide Effecitve Leadership and Commitment | Effective Leadership and Commitment Checklist | Preconstruction
01 35 63.01 | Sustainability Requirements | 1.5.B.8.c |  | Sustainable Design - Informational | RA 1.4 Reduce Construction Waste | Reduce Construction Waste Checklist | Preconstruction
01 35 63.01 | Sustainability Requirements | 1.5.B.8.d |  | Sustainable Design - Informational | RA 2.2 Reduce Construction Energy Consumption | Reduce Construction Energy Checklist | Preconstruction
01 35 63.01 | Sustainability Requirements | 1.5.B.8.e |  | Sustainable Design - Informational | RA 3.3 Reduce Construction Water Consumption | Reduce Construction Water Checklist | Preconstruction
01 35 63.01 | Sustainability Requirements | 1.5.B.8.f |  | Sustainable Design - Informational | CR 1.3 Reduce Air Polluttant Emissions | Reduce Air Pollutant Emissions Checklist | Preconstruction
01 35 63.01 | Sustainability Requirements | 1.5.B.8.g |  | Sustainable Design - Informational | Credit Reference and Description | Credit Checklist | Preconstruction
01 55 26 | Maintenance and Protection of Traffic | 1.5.B.9.a |  | Special Procedures - Informational | Maintenance of Traffic Plan | Sketch of planned lane closers, signage locations, flagging locations as required, and proposed dates of shutdown. | Preconstruction
01 55 26 | Maintenance and Protection of Traffic | 1.5.B.9.b |  | Special Procedures - Informational | Truck Haul Routes | Submit as required. Submit sketch of proposed haul routes. | Preconstruction
01 55 26 | Maintenance and Protection of Traffic | 1.5.B.9.c |  | Special Procedures - Informational | Permit Submittals | Submittal applicable permits for the Project including Barricade Permit, County Permit, and Cut Permit. | Preconstruction
01 57 13 | Temporary Erosion and Sedimentation Control | 1.5.A.1.a |  | Product Data - Action | Erosion Controls - Product Data | Product Data of all proposed erosion control products | Preconstruction
01 57 13 | Temporary Erosion and Sedimentation Control | 1.5.B.5.a | 1.5.B.5.a.1. | Field Quality Control - Informational | Erosion Control Inspection Log | Maintenance and inspection log for all erosion control products on-site | Construction
01 57 13 | Temporary Erosion and Sedimentation Control | 1.5.B.9.a |  | Special Procedures - Informational | Erosion Control Plan | Location of staging and maintenance of site erosion controls. Approximate areas of soil disturbance not on Drawings. Locations and details of temporary settlement basins, washout areas, and construction entrances. | Preconstruction
01 71 16.13 | Video Documentation of Conditions | 1.5.B.5.a |  | Field Quality Control - Informational | Pre-Construction Video Documentation | Video file showing site pre-construction conditions. | Preconstruction
01 71 23 | Field Engineering | 1.5.B.5.a |  | Field Quality Control - Informational | Field Engineering - Daily Reports | Notes about daily construction activities. | Construction
01 71 23 | Field Engineering | 1.5.B.5.b |  | Field Quality Control - Informational | Surveying | Submit certified survey in accordance with this Section. | Preconstruction
01 71 23 | Field Engineering | 1.5.B.6.a |  | Qualifications Statements - Informational | Field Engineer Qualifications | Name, employer, and professional address. When requested by Engineer, submit qualifications, including resume’. | Preconstruction
01 71 23 | Field Engineering | 1.5.B.6.b |  | Qualifications Statements - Informational | Surveyor Qualifications | Name, employer, and professional address. When requested by Engineer, submit qualifications, including resume’. | Preconstruction
01 75 11 | Checkout and Startup Procedures | 1.5.B.2.a |  | Test and Evaluation Reports - Informational | Commissioning Information | Information for each piece of equipment, as listed in Paragraph 1.6.A.1 | Closeout
01 75 11 | Checkout and Startup Procedures | 1.5.B.9.a |  | Special Procedures - Informational | Commissioning Plan | Proposed procedures for checkout and startup of equipment | Construction
01 77 00 | Closeout Procedures | 1.5.C.2 |  | Record Documentation - Closeout | Record Documents | Annotated Drawings and Project Manuals marked up to show the actual products use and locations of concealed work and utilities. | Closeout
01 77 00 | Closeout Procedures | 1.5.C.6 |  | Bonds - Closeout | Special Bonds | Special bonds, guarantees, and service agreements | Closeout
01 77 00 | Closeout Procedures | 1.5.C.9 |  | Consent of Surety to Final Payment - Closeout | Consent of Surety to Final Payment | As required in the General Conditions | Closeout
01 77 00 | Closeout Procedures | 1.5.C.10 |  | Releases or Waivers of Liens and Claims - Closeout | Releases or Waivers of Liens and Claims | As required in the General Conditions | Closeout
01 77 00 | Closeout Procedures | 1.5.C.11 |  | Releases from Agreements - Closeout | Releases from Agreements | As required in the General Conditions | Closeout
01 77 00 | Closeout Procedures | 1.5.C.12 |  | American Iron & Steel Requirement - Closeout | American Iron and Steel Requirement | As required in the General Conditions | Closeout
01 78 23 | Operation and Maintenance Data | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Preliminary - Operational and Maintenance Data | O&M Data for materials and equipment | Closeout
01 78 23 | Operation and Maintenance Data | 1.5.C.1.b |  | Operation and Maintenance Data - Closeout | Final - Operational and Maintenance Data | O&M Data for materials and equipment | Closeout
01 78 39 | Project Record Documents | 1.5.C.2.a |  | Record Documentation - Closeout | Preliminary Record Drawings | Color scan of original Record Documents including field edits and revisions. | Closeout
01 78 39 | Project Record Documents | 1.5.C.2.b |  | Record Documentation - Closeout | Final Record Documents - Electronic Notes | Electronically edited set of Record Drawings, revisions and notes added to PDF type document. | Closeout
01 78 39 | Project Record Documents | 1.5.C.2.c |  | Record Documentation - Closeout | Original Record Drawings - Field Copy | Original hard copy used to record changes during the Work | Closeout
01 78 39 | Project Record Documents | 1.5.C.2.d |  | Record Documentation - Closeout | Final Record Drawings -Electronically Revised | Submit as requested, Electronically revised Contract Drawings, in CAD format, that reflects changes during the work. | Closeout
01 78 39 | Project Record Documents | 1.5.C.2.e |  | Record Documentation - Closeout | Contractor Field Survey | Submit as requested | Closeout
01 78 39 | Project Record Documents | 1.5.C.5.a |  | Software - Closeout | Programming Files | Narrative description of program | Closeout
01 79 23 | Instruction of Operation and Maintenance Personnel | 1.5.B.1.a |  | Certificates - Informational | Certificate of Instructional Services | Submit Certificate of Instructional Services as training have been completed | Closeout
01 79 23 | Instruction of Operation and Maintenance Personnel | 1.5.C.3.a |  | Training Program - Closeout | Training Program | Training manual for operations staff and instructores guide. | Closeout
01 79 23 | Instruction of Operation and Maintenance Personnel | 1.5.C.3.b |  | Trainer Resume - Closeout | Trainer Resumer with references | Resumes with references of each instructor for each equipment | Closeout
Division 03 - Concrete
03 00 05 | Concrete | 1.5.A.1.a |  | Product Data - Action | Concrete Materials - Product Data | Supplier product data on concrete materials, accessories, grout and mix designs for Work. | Construction
03 00 05 | Concrete | 1.5.A.1.b |  | Product Data - Action | Admixture and Bonding Agents - Manufacturers' Specifications | Manufacturers'' specification on application and instruction for proprietary materials. | Construction
03 00 05 | Concrete | 1.5.A.2.a |  | Shop Drawings - Action | Concrete Reinforcing Drawings | Drawings showing the placement and types of reinforcement | Construction
03 00 05 | Concrete | 1.5.A.2.b |  | Shop Drawings - Action | Concrete Joint Placement Drawings | Drawings showing the placement and type of concrete joints | Construction
03 00 05 | Concrete | 1.5.A.2.c |  | Shop Drawings - Action | Individual Forms Locations | Submit as requested, Drawings indicating general construction of individual forms | Construction
03 00 05 | Concrete | 1.5.B.4.a |  | Source Quality Control - Informational | Laboratory Trial Batch Reports | Laboratory Test Reports for concrete cylinders, materials, and mix design tests | Construction
03 00 05 | Concrete | 1.5.B.4.b | 1.5.B.4.b.1. | Source Quality Control - Informational | Delivery Tickets | Copies of all concrete delivery tickets for each load of concrete delivered to site. | Construction
03 00 05 | Concrete | 1.5.B.5.a | 1.5.B.5.a.1. | Field Quality Control - Informational | Concrete Field Quality Control Tests | All test reports as listed in Article 3.9B | Construction
Division 05 - Metals
05 56 00 | Metal Castings | 1.5.A.1.a |  | Product Data - Action | Metal Castings - Product Data | Manufacturer's information on all products specified in specification. | Construction
05 56 00 | Metal Castings | 1.5.B.6.a |  | Qualifications Statements - Informational | Metal Castings - Qualifications Statement | Submit as required, if contractor is submitting on an unlisted manufacturer. | Construction
Division 26 - Electrical
26 05 05 | General Provisions for Electrical Systems | 1.5.A.1.a |  | Product Data - Action | Electrical System Product Data | Manufacturer's product data on electrical systems | Construction
26 05 05 | General Provisions for Electrical Systems | 1.5.A.2.a |  | Shop Drawings - Action | Internal Wiring Diagram and Drawings | Internal wiring diagram and drawings indicating all connections to components and numbered terminals for external connections. | Construction
26 05 05 | General Provisions for Electrical Systems | 1.5.A.2.b |  | Shop Drawings - Action | Dimensioned Plan, Section, Elevations, and Panel Layouts | Dimensioned plan, section, elevations, and panel layouts showing means for mounting, conduit connection, and grounding. | Construction
26 05 05 | General Provisions for Electrical Systems | 1.5.A.2.c |  | Shop Drawings - Action | Components List | List of components including manufacturer’s name and catalog number (or part number) for each. | Construction
26 05 05 | General Provisions for Electrical Systems | 1.5.A.2.d |  | Shop Drawings - Action | Point-to-Point Interconnection Wiring Diagrams | Point-to-Point Interconnection Wiring Diagrams | Construction
26 05 05 | General Provisions for Electrical Systems | 1.5.B.1.a |  | Certificates - Informational | Manufacturers' Certificate of Compliance with Standards | Manufacturers' Certificate of Compliance with Standards | Construction
26 05 05 | General Provisions for Electrical Systems | 1.5.B.2.a |  | Test and Evaluation Reports - Informational | Electrical Systems Test Procedures | Proposed testing procedures and testing limitations for Source Quality Control testing and Field Quality Control testing. | Construction
26 05 05 | General Provisions for Electrical Systems | 1.5.B.3.a |  | Manufacturers Instructions - Informational | Electrical Systems - Manufacturers' Instructions | Installation data and instructions for handling, starting-up, and troubleshooting. | Construction
26 05 05 | General Provisions for Electrical Systems | 1.5.B.4.a |  | Source Quality Control - Informational | Electrical Systems Source Quality Control Test Results | Results for required shop testing. | Construction
26 05 05 | General Provisions for Electrical Systems | 1.5.B.5.a |  | Field Quality Control - Informational | Electrical Systems Field Quality Control Test Results | Results for field shop testing. | Construction
26 05 05 | General Provisions for Electrical Systems | 1.5.B.6.a |  | Qualifications Statements - Informational | Electrical Subcontractor Qualification Statement | Qualification Statement for Electrical subcontractor | Construction
26 05 05 | General Provisions for Electrical Systems | 1.5.C.2.a |  | Record Documentation - Closeout | Electrical Systems - Record Drawings | System record drawings, point-to-point interconnection wiring diagram drawings, final field equipment and field installation information, and system supplier wiring diagrams. | Closeout
26 05 13 | Medium Voltage Cables | 1.5.A.1.a |  | Product Data - Action | Medium Voltage Cables - Product Data | Manufacturer’s literature and technical information indicating compliance with the Contract Documents. | Construction
26 05 13 | Medium Voltage Cables | 1.5.A.2.a |  | Shop Drawings - Action | Medium Voltage Cables - Shop Drawings | Listing of locations where splices are proposed. | Construction
26 05 13 | Medium Voltage Cables | 1.5.A.4. |  | Delegated Design - Action | Medium Voltage Cables - Delegated Design | Project specific cable pulling calculations from cable manufacturer. | Construction
26 05 13 | Medium Voltage Cables | 1.5.B.4.a |  | Source Quality Control - Informational | Medium Voltage Cables - Source Quality Control | Submit results of factory tests, including testing procedures utilized. | Construction
26 05 13 | Medium Voltage Cables | 1.5.B.5.a |  | Field Quality Control - Informational | Medium Voltage Cables - Field Quality Control | Submit results of Field Quality Control testing. Include testing procedures utilized. | Construction
26 05 13 | Medium Voltage Cables | 1.5.B.6.a |  | Qualifications Statements - Informational | Medium Voltage Cables - Qualifications of Splicing and Termination Personnel | Qualifications of splicing and termination personnel. | Construction
26 05 13 | Medium Voltage Cables | 1.5.B.6.b |  | Qualifications Statements - Informational | Medium Voltage Cables - Qualifications of Independent Testing Agency | Qualifications of independent testing agency. | Construction
26 05 13 | Medium Voltage Cables | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Medium Voltage Cables - Operation and Maintenance Data | Maintenance data for cables and accessories, manufacturer's written instructions for periodic tests of cables in service, operating instructions for fault indicators and separable insulated connectors and their accessories, and submit in accordance with Section 01 78 23. | Closeout
26 05 13 | Medium Voltage Cables | 1.5.C.2.a |  | Record Documentation - Closeout | Medium Voltage Cables - Record Documentation | Include actual location and routing of medium voltage cable installations. | Closeout
26 05 19 | Low-Voltage Electrical Power Conductors and Cables | 1.5.A.1.a |  | Product Data - Action | Low-Voltage Electrical Power Conductors and Cables - Product Data | Manufacturer’s literature, specifications, and engineering data for low voltage insulated cable proposed for use. | Construction
26 05 19 | Low-Voltage Electrical Power Conductors and Cables | 1.5.B.1.a |  | Certificates - Informational | Low-Voltage Electrical Power Conductors and Cables - Certifications | Certification by the manufacturer that the conductors and cables conform to the requirements of the drawings and specifications. Certification by the Contractor that the conductors and cables have been properly installed, adjusted, and tested. | Construction
26 05 19 | Low-Voltage Electrical Power Conductors and Cables | 1.5.B.5.a |  | Field Quality Control - Informational | Low-Voltage Electrical Power Conductors and Cables - Field Quality Control Submittals | Written results of field insulation resistance tests. | Construction
26 05 23 | Instrumentation Cable | 1.5.A.1.a |  | Product Data - Action | Instrumentation Cable-Product Data | Manufacturer’s technical information for instrumentation cables and communications cables proposed. | Construction
26 05 23 | Instrumentation Cable | 1.5.A.2.a |  | Shop Drawings - Action | Cable Tray Layout - Shop Drawings | For cable tray layout, showing cable tray route to scale, with relationship between the tray and adjacent structural, electrical, and mechanical elements. | Construction
26 05 23 | Instrumentation Cable | 1.5.B.5.a |  | Field Quality Control - Informational | Instrumentation Cables - Field Quality Control | Written report of results of Field Quality Control testing specified in this Section. | Construction
26 05 23 | Instrumentation Cable | 1.5.B.6.a |  | Qualifications Statements - Informational | Independent Testing Agency Qualification Data | Proof of independent testing agencies qualifications for BICSI as an RCDD to supervise on-site testing. | Construction
26 05 26 | Grounding and Bonding for Electrical Systems | 1.5.A.1.a |  | Product Data - Action | Grounding and Bonding for Electrical Systems - Product Data | Manufacturer’s technical information for grounding materials proposed for use. | Construction
26 05 26 | Grounding and Bonding for Electrical Systems | 1.5.A.2.a |  | Shop Drawings - Action | Grounding and Bonding for Electrical Systems - Shop Drawings | Listings of grounding connector types identifying where each will be used, layouts of each structure's ground grid, and test point construction details. | Construction
26 05 26 | Grounding and Bonding for Electrical Systems | 1.5.B.1.a |  | Certificates - Informational | Grounding and Bonding for Electrical Systems - Certificates | Certificates for field testing agency, signed by Contractor, certifying that agency complies with requirements specified in Quality Assurance Section Above. | Construction
26 05 26 | Grounding and Bonding for Electrical Systems | 1.5.B.5.a |  | Field Quality Control - Informational | Grounding and Bonding for Electrical Systems - Testing Plans | Ground resistance test procedure. | Construction
26 05 26 | Grounding and Bonding for Electrical Systems | 1.5.B.5.b |  | Field Quality Control - Informational | Grounding and Bonding for Electrical Systems - Field Quality Control | Results of ground resistance tests at each test point. | Construction
26 05 26 | Grounding and Bonding for Electrical Systems | 1.5.C.2.a |  | Record Documentation - Closeout | Grounding and Bonding for Electrical Systems - Record Documentation | Reference 01 78 39 for requirements of plans showing actual locations of grounding features. | Closeout
26 05 29 | Hangers and Supports for Electrical Systems | 1.5.A.1.a |  | Product Data - Action | Hangers and Supports for Electrical Systems - Product Data | Submit manufacturer's data as specified, pictorial views and descriptions as specified, and documentation that confirms product compatibility with Laws and Regulations | Construction
26 05 29 | Hangers and Supports for Electrical Systems | 1.5.A.2.a |  | Shop Drawings - Action | Hangers and Supports for Electrical Systems - Shop Drawings | Detailed installation drawings showing dimensions and compatibility with proposed layout. | Construction
26 05 29 | Hangers and Supports for Electrical Systems | 1.5.B.1.a |  | Certificates - Informational | Hangers and Supports for Electrical Systems - Certificates | Submit certifications required under this section. | Construction
26 05 33 | Raceways and Boxes for Electrical Systems | 1.5.A.1.a |  | Product Data - Action | Raceways and Boxes - Product Data | Manufacturer’s catalog cuts and product data for conduit, fittings, and appurtenances. | Construction
26 05 33 | Raceways and Boxes for Electrical Systems | 1.5.A.2.a |  | Shop Drawings - Action | Raceways and Boxes - Assembly Details | Assembly details of conduit racks and other conduit support systems. | Construction
26 05 33 | Raceways and Boxes for Electrical Systems | 1.5.A.2.b |  | Shop Drawings - Action | Raceways and Boxes - Layout Drawings | Submit layout drawings as specified. | Construction
26 05 33 | Raceways and Boxes for Electrical Systems | 1.5.B.3.a |  | Manufacturers Instructions - Informational | Raceways and Boxes - Manufacturers' Instructions | When requested by Engineer, provide copies of manufacturer’s recommendations for handling and installing products. | Construction
26 05 33 | Raceways and Boxes for Electrical Systems | 1.5.B.5.a |  | Field Quality Control - Informational | Raceways and Boxes - Field Quality Control | When requested by Engineer, provide copies of results of specified Site quality control testing. | Construction
26 05 33 | Raceways and Boxes for Electrical Systems | 1.5.C.2.a |  | Record Documentation - Closeout | Raceways and Boxes - Record Drawings | Show actual routing of exposed and concealed conduit runs in record documents in accordance with Section 01 78 39, Project Record Documents. | Closeout
26 05 43 | Underground Ducts and Raceways for Electrical Systems | 1.5.A.1.a |  | Product Data - Action | Underground Ducts and Raceways - Manufacturer's Technical Documents | Manufacturer’s technical information, specifications, and literature for manholes, handholes, castings, and accessories proposed for use. Duct-bank materials, including separators and miscellaneous components. Ducts and conduits and their accessories, including elbows, end bells, bends, fittings, and solvent cement. Warning tape product data. | Construction
26 05 43 | Underground Ducts and Raceways for Electrical Systems | 1.5.A.2.a |  | Shop Drawings - Action | Layout of Manhole Electrical Systems | Where manholes have extensive electrical systems and supports for electrical systems, submit for each plans, sections, and details indicating proposed layout of such materials and equipment in each manhole. Provide info for Factory-Fabricated Handholes and Boxes Other Than Precast Concrete and Precast or Factory-Fabricated Underground Utility Structures. Include plans, elevations, sections, details, attachments to other work, and accessories. | Construction
26 05 43 | Underground Ducts and Raceways for Electrical Systems | 1.5.A.2.b |  | Shop Drawings - Action | Duct-Bank Coordination Drawings | Show duct profiles and coordination with other utilities and underground structures. | Construction
26 05 43 | Underground Ducts and Raceways for Electrical Systems | 1.5.B.1.a |  | Certificates - Informational | Underground Ducts and Raceways - Product Certificates | Product data for concrete and steel used in precast concrete manholes and handholes, as required by ASTM C 858. | Construction
26 05 43 | Underground Ducts and Raceways for Electrical Systems | 1.5.C.2.a |  | Record Documentation - Closeout | Underground Ducts and Raceways - Record Drawings | Include actual routing of underground duct bank runs on record documents in accordance with Section 01 78 39, Project Record Documents. | Closeout
26 05 43 | Underground Ducts and Raceways for Electrical Systems | 1.5.D.2.a |  | Extra Stock Materials - Maintenance Material | Underground Ducts and Raceways - Extra Stock Materials | Cable-support stanchions, arms, insulators, and associated fasteners in quantities equal to ten (10) percent of quantity of each item installed. | Construction
26 05 53 | Identification For Electrical Systems | 1.5.A.1.a |  | Product Data - Action | Identification For Electrical Systems -Product Data | Manufacturer’s literature, cut sheets, specifications, dimensions and technical data for all products proposed under this Section. | Construction
26 05 53 | Identification For Electrical Systems | 1.5.A.2.a |  | Shop Drawings - Action | Identification For Electrical Systems - Shop Drawings | Description and listing of proposed electrical identification and electrical identification devices for associated equipment or systems. Conduit and wire identification numbering system and equipment signage | Construction
26 05 53 | Identification For Electrical Systems | 1.5.A.2.b |  | Shop Drawings - Action | Identification For Electrical Systems - Schedule | An index of nomenclature of electrical equipment and system components used in identification signs and labels. | Construction
26 05 53 | Identification For Electrical Systems | 1.5.A.3.a |  | Samples - Action | Identification For Electrical Systems - Samples | For each type of label and sign to illustrate size, colors, lettering style, mounting provisions, and graphic features of identification products. | Construction
26 09 13 | Electrical Power Monitoring | 1.5.A.1.a |  | Product Data - Action | Electrical Power Monitoring Product Data | Manufacturer’s literature and technical information indicating compliance with the Contract Documents | Construction
26 09 13 | Electrical Power Monitoring | 1.5.B.3.a |  | Manufacturers Instructions - Informational | Electrical Power Monitoring Installation Instructions | A copy of the manufacturer’s installation instructions, including receiving, handling and storage instructions. | Construction
26 09 13 | Electrical Power Monitoring | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Electrical Power Monitoring Operation and Maintenance Data | Energy or power quality monitor installation instructions and User Manual. Parameter listing. IP address and Network Diagram. | Closeout
26 09 13 | Electrical Power Monitoring | 1.5.C.3.a |  | Training Material - Informational | Electrical Power Monitoring Training Material | Proposed Training Material; Student Material and Instructor guide. | Closeout
26 09 13 | Electrical Power Monitoring | 1.5.C.3.c |  | Training Instructor(s) resume(s) | Electrical Power Monitoring Resumes | Resumes with references of each instructor for the traning material. | Closeout
26 09 13 | Electrical Power Monitoring | 1.5.C.4.a |  | Warranty Documentation - Closeout | Electrical Power Monitoring - Manufacturers' Warranty | Written copy of warranty from manufacturer complying with this document. | Closeout
26 09 13 | Electrical Power Monitoring | 1.5.C.5.a |  | Software - Closeout | Electrical Power Monitoring - Software | Copy of latest firmware/software on flash drive | Closeout
26 09 13 | Electrical Power Monitoring | 1.5.D.1.a |  | Spare Parts - Maintenance Material | Electrical Power Monitoring - Spare Parts | One spare set of fuses and shorting blank for each type used for installation | Construction
26 09 23 | Lighting Control Devices | 1.5.A.1.a |  | Product Data - Action | Lighting Control Devices - Product Data | Product Data for each type of lighting control device | Construction
26 09 23 | Lighting Control Devices | 1.5.A.2.a |  | Shop Drawings - Action | Lighting Control Devices - Shop Drawings | Listing, location, and rating for each sensor to be furnished. Drawings including, outline drawings with dimensions, interconnection diagrams, and diagrams for power, signal, and control wiring | Construction
26 09 23 | Lighting Control Devices | 1.5.B.3.a |  | Manufacturers Instructions - Informational | Lighting Control Devices - Manufacturers Instructions | Installation and programming instructions for each type | Construction
26 09 23 | Lighting Control Devices | 1.5.B.4.a |  | Source Quality Control - Informational | Lighting Control Devices - Source Quality Control | Results of required Source Quality Control tests and inspections. | Construction
26 09 23 | Lighting Control Devices | 1.5.B.5.a |  | Field Quality Control - Informational | Lighting Control Devices - Field Quality Control | Results of required Field Quality Control tests and inspections. | Construction
26 09 23 | Lighting Control Devices | 1.5.B.6.a |  | Qualifications Statements - Informational | Lighting Control Devices - Qualifications Statements | Submit manufacturer qualifications when requested by Engineer | Construction
26 09 23 | Lighting Control Devices | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Lighting Control Devices - Operation and Maintenance Data | Complete installation, operation and maintenance manuals including test reports, maintenance data and schedules, and description of operation | Closeout
26 09 23 | Lighting Control Devices | 1.5.C.4.a |  | Warranty Documentation - Closeout | Lighting Control Devices - warranty Documentation | Warranty documentation for each type | Closeout
26 12 00 | Medium Voltage Transformers | 1.5.A.1.a |  | Product Data - Action | Medium Voltage Transformers Product Data | Manufacturer's technical information. Transformer Data. Include dimensional plans, sections and elevation views. Minimum clearances and installed dvices and features. | Construction
26 12 00 | Medium Voltage Transformers | 1.5.A.1.b |  | Product Data - Action | Anchorage System Information | Anchorage system information with load calculations | Construction
26 12 00 | Medium Voltage Transformers | 1.5.A.2.a |  | Shop Drawings - Action | Transformer Layout | Transformer layout including dimensions and locations of anchors. | Construction
26 12 00 | Medium Voltage Transformers | 1.5.B.1.a |  | Certificates - Informational | Seismic Certification |  | Construction
26 12 00 | Medium Voltage Transformers | 1.5.B.4.a |  | Source Quality Control - Informational | Transformer Factory Test Reports | Transformer Factory Test Report | Construction
26 12 00 | Medium Voltage Transformers | 1.5.B.5.a |  | Field Quality Control - Informational | Transformer Field Test Reports | Transformer Field Test Report | Construction
26 12 00 | Medium Voltage Transformers | 1.5.B.6.a |  | Qualifications Statements - Informational | Qualifications Statements of Manufacturer | Submit as requested | Construction
26 12 00 | Medium Voltage Transformers | 1.5.B.9.a |  | Special Procedures - Informational | Proposed factory test methods, procedures, and apparatus | Proposed factory test methods, procedures, and apparatus | Construction
26 12 00 | Medium Voltage Transformers | 1.5.B.9.b |  | Special Procedures - Informational | Proposed field test methods, procedures, and apparatus | Proposed field test methods, procedures, and apparatus | Construction
26 12 00 | Medium Voltage Transformers | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Medium Voltage Transformers – Operation and Maintenance Data | In accordance with Section 01 78 23 | Closeout
26 19 23 | Medium-Voltage Variable Frequency Drives | 1.5.A.1.a |  | Product Data - Action | Medium-Voltage Variable Frequency Drives - Product Data | Manufacturer's technical information, catalog cuts and product literature | Construction
26 19 23 | Medium-Voltage Variable Frequency Drives | 1.5.A.2.a |  | Shop Drawings - Action | Medium-Voltage Variable Frequency Drives - Shop Drawings | Detailed diagrams and dimensional information | Construction
26 19 23 | Medium-Voltage Variable Frequency Drives | 1.5.B.1.a |  | Certificates - Informational | Medium-Voltage Variable Frequency Drives - Certificates | low-voltage variable frequency drive manufacturer and motor manufacturer compatibility certification letters | Construction
26 19 23 | Medium-Voltage Variable Frequency Drives | 1.5.B.2.a |  | Test and Evaluation Reports - Informational | Medium-Voltage Variable Frequency Drives - Testing Plans | Description of shop and field testing measures | Construction
26 19 23 | Medium-Voltage Variable Frequency Drives | 1.5.B.4.a |  | Source Quality Control - Informational | Medium-Voltage Variable Frequency Drives - Source Quality Control | Results of source quality control tests and inspections | Construction
26 19 23 | Medium-Voltage Variable Frequency Drives | 1.5.B.5.a |  | Field Quality Control - Informational | Medium-Voltage Variable Frequency Drives - Field Quality Control | Results of field quality control tests and inspections | Construction
26 19 23 | Medium-Voltage Variable Frequency Drives | 1.5.B.6.a |  | Qualifications Statements - Informational | Manufacturer Qualifications Statement | When requested by engineer | Construction
26 19 23 | Medium-Voltage Variable Frequency Drives | 1.5.B.7.a |  | Manufacturer Reports - Informational | Medium-Voltage Variable Frequency Drives - Manufacturer Reports | Results of manufacturer site visits | Construction
26 19 23 | Medium-Voltage Variable Frequency Drives | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Medium-Voltage Variable Frequency Drives - Operations and Maintenance Data | Complete installation, operation and maintenance manuals | Closeout
26 19 23 | Medium-Voltage Variable Frequency Drives | 1.5.C.2.a |  | Record Documentation - Closeout | Medium-Voltage Variable Frequency Drives - Record Documentation | Provide record documentation as stated in the contract documents | Closeout
26 19 23 | Medium-Voltage Variable Frequency Drives | 1.5.C.3.a |  | Training Material - Informational | Medium-Voltage Variable Frequency Drives Training Material | Proposed Training Material; Student Material and Instructor guide. | Closeout
26 19 23 | Medium-Voltage Variable Frequency Drives | 1.5.C.3.c |  | Training Instructor(s) resume(s) | Medium-Voltage Variable Frequency Drives Resumes | Resumes with references of each instructor for the traning material. | Closeout
26 22 00 | Low-Voltage Transformers | 1.5.A.1.a |  | Product Data - Action | Low Voltage Transformers Product Data | Transformer Data - and dimensioned plans, section and elevation views. | Construction
26 22 00 | Low-Voltage Transformers | 1.5.A.2.a |  | Shop Drawings - Action | Schedule of Low Voltage Transformers | Schedule, ratings, and other required technical data. | Construction
26 22 00 | Low-Voltage Transformers | 1.5.A.2.b |  | Shop Drawings - Action | Low Voltage Transformer Locations | Include pad layout, dimensions, and appurtenances | Construction
26 22 00 | Low-Voltage Transformers | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Low-Voltage Transformers – Operation and Maintenance Data | In accordance with Section 01 78 23, include acceptable test reports, maintenance data and schedules, and wiring diagrams | Closeout
26 24 13 | Switchboards | 1.5.A.1.a |  | Product Data - Action | Manufacturer's Technical Information | Manufacturer’s technical information, specifications and time current curves for protective devices. | Construction
26 24 13 | Switchboards | 1.5.A.2.a |  | Shop Drawings - Action | Switchboard Shop Drawings | Details on switchboards | Construction
26 24 13 | Switchboards | 1.5.B.1.a |  | Certificates - Informational | Switchboard - Certificates | Seismic requirements | Construction
26 24 13 | Switchboards | 1.5.B.4.a |  | Source Quality Control - Informational | Switchboard Source Quality Control Reports | Manufacturer's shop testing | Construction
26 24 13 | Switchboards | 1.5.B.5.a |  | Field Quality Control - Informational | Switchboard Field Quality Control Reports | Field testing results | Construction
26 24 13 | Switchboards | 1.5.B.6.a |  | Qualifications Statements - Informational | Manufacturer Qualifications Statements | When requested by Engineer | Construction
26 24 13 | Switchboards | 1.5.B.7.a |  | Manufacturer Reports - Informational | Switchboard Manufacturer Report | written report of results of each visit to Site by Supplier’s service technician | Construction
26 24 13 | Switchboards | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Switchboards - Operation and Maintenance Data | Include test reports, maintenance data, schedules, and record drawings of control schematics. | Closeout
26 24 13 | Switchboards | 1.5.C.3.a |  | Training Material - Informational | Switchboards Training Material | Proposed Training Material; Student Material and Instructor guide. | Closeout
26 24 13 | Switchboards | 1.5.C.3.c |  | Training Instructor(s) resume(s) | Switchboards Resumes | Resumes with references of each instructor for the traning material. | Closeout
26 24 16 | Panelboards | 1.5.A.1.a |  | Product Data - Action | Panelboards Product Data | Panelboard technical information, specifications and product literature. | Construction
26 24 16 | Panelboards | 1.5.A.2.a |  | Shop Drawings - Action | Listing of Panelboards and Proposed Locations | Detailed information on panelboards including locations, device information, breakers etc. | Construction
26 24 16 | Panelboards | 1.5.A.2.b |  | Shop Drawings - Action | Panelboards Schedule | For installation in panelboards. Submit final versions after load balancing. | Construction
26 24 16 | Panelboards | 1.5.B.5.a |  | Field Quality Control - Informational | Panelboards Testing Plan, Procedures and Results | Test procedures, results and corrective action for failed test. | Construction
26 24 16 | Panelboards | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Panelboard Operation and Maintenance Data | Submit O&M Data in accordance with 01 78 23 | Closeout
26 24 16 | Panelboards | 1.5.C.2.a |  | Record Documentation - Closeout | Panelboard Record Documentation | an electronic modifiable copy of each updated and/or new panel board schedule with date of change(s). | Closeout
26 24 16 | Panelboards | 1.5.D.1.a |  | Spare Parts - Maintenance Material | Fuses for Fused Power Circuit Devices | 10 percent of quantity installed for each size and type, but no fewer than three of each size and type. | Construction
26 24 19 | Motor Control Centers | 1.5.A.1.a |  | Product Data - Action | Motor Control Centers Product Data | Specifications, cut sheets, dimensions and technical data. | Construction
26 24 19 | Motor Control Centers | 1.5.A.2.a |  | Shop Drawings - Action | Motor Control Center Shop Drawings | Detailed drawings and information on locations, terminal connection points, one-line diagrams. | Construction
26 24 19 | Motor Control Centers | 1.5.B.2.a |  | Test and Evaluation Reports - Informational | Supplier Report | Reports from Suppliers service technician. | Construction
26 24 19 | Motor Control Centers | 1.5.B.3.a |  | Manufacturers Instructions - Informational | Supplier Instructions | Info on shipping, handling installation and start up. | Construction
26 24 19 | Motor Control Centers | 1.5.B.4.a |  | Source Quality Control - Informational | Motor Control Centers - Source Quality Control Reports | Reports of completed factory testing | Construction
26 24 19 | Motor Control Centers | 1.5.B.5.a |  | Field Quality Control - Informational | Motor Control Centers - Field Quality Control Reports | Reports of completed field testing | Construction
26 24 19 | Motor Control Centers | 1.5.B.6.a |  | Qualifications Statements - Informational | Motor Control Centers - Qualifications Statements | Independent testing firm and manufacturer when requested by Engineer | Construction
26 24 19 | Motor Control Centers | 1.5.B.7.a |  | Manufacturer Reports - Informational | Motor Control Centers - Manufacturer Reports | written report of results of each visit to Site by Supplier’s service technician, including purpose and time of visit, tasks performed, and results obtained | Construction
26 24 19 | Motor Control Centers | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Motor Control Centers - Operation and Maintenance Data | O&M manuals and comply with 01 78 23 | Closeout
26 24 19 | Motor Control Centers | 1.5.C.2.a |  | Record Documentation - Closeout | Motor Control Centers - Record Documentation | Provide record documentation as stated in the contract documents | Closeout
26 24 19 | Motor Control Centers | 1.5.C.4.a |  | Warranty Documentation - Closeout | Motor Control Centers - Warranty Documentation | Provide the warranty information as stated in the contract documents | Closeout
26 24 19 | Motor Control Centers | 1.5.D.1.a |  | Spare Parts - Maintenance Material | Motor Control Centers - Spare Parts | Provide fuses, lamps and touch up paint. | Construction
26 24 19 | Motor Control Centers | 1.5.C.3.a |  | Training Material - Informational | Motor Control Centers Training Material | Proposed Training Material; Student Material and Instructor guide. | Closeout
26 24 19 | Motor Control Centers | 1.5.C.3.c |  | Training Instructor(s) resume(s) | Motor Control Centers Resumes | Resumes with references of each instructor for the traning material. | Closeout
26 24 19 | Motor Control Centers | 1.5.D.1.b |  | Spare Parts - Maintenance Material | Motor Control Center Spare Parts Recommendations | List of additional recommended spare parts. | Construction
26 27 26 | Wiring Devices | 1.5.A.1.a |  | Product Data - Action | Wiring Devices - Product Data | For each type of product | Construction
26 27 26 | Wiring Devices | 1.5.B.2.a |  | Test and Evaluation Reports - Informational | Wiring Devices - Test and Evaluation Reports | Results of required test and evaluation reports | Construction
26 27 26 | Wiring Devices | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Wiring Devices - Operation and Maintenance Data | Complete installation, operation and maintenance manuals including all manufacturer's packing label warnings and instruction manuals | Closeout
26 28 13 | Fuses | 1.5.A.1.a |  | Product Data - Action | Fuses - Product Data | For each type | Construction
26 28 13 | Fuses | 1.5.A.2.a |  | Shop Drawings - Action | Fuses - Shop Drawings | For each type include: dimensions and technical data, current limitation curves, current coordination curves, charts and related data | Construction
26 28 13 | Fuses | 1.5.B.6.a |  | Qualifications Statements - Informational | Manufacturer Qualifications Statements | When requested by engineer | Construction
26 28 13 | Fuses | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Fuses - Operation and Maintenance Data | Complete installation, operation and maintenance manuals, recommended spare parts and extra stock materials. Comply with Section 01 78 23, Operations and Maintneance Data. | Closeout
26 28 13 | Fuses | 1.5.C.4.a |  | Warranty Documentation - Closeout | Manufacturer's Warranty Documentation | Manufacturers' Warranty Documentation | Closeout
26 28 13 | Fuses | 1.5.D.1.a |  | Spare Parts - Maintenance Material | Fuses - Spare Parts | One set of spare fuses for each size and type to be installed | Construction
26 28 13 | Fuses | 1.5.D.3.a |  | Tools - Maintenance Material | Fuses - Tools | One set if fuse pullers for each size and type installed | Construction
26 28 16 | Enclosed Switches and Circuit Breakers | 1.5.A.1.a |  | Product Data - Action | Switches and Circuit Breakers - Product Data | Specifications, cut sheets, dimensions and technical data. | Construction
26 28 16 | Enclosed Switches and Circuit Breakers | 1.5.A.2.a |  | Shop Drawings - Action | Switches and Circuit Breakers - Shop Drawings | Detailed drawings and information on locations, terminal connection points, one-line diagrams. | Construction
26 28 16 | Enclosed Switches and Circuit Breakers | 1.5.B.1.a |  | Certificates - Informational | Switches and Circuit Breakers - Manufacturer Certificates | Manufacturer’s certification of completed installation. | Construction
26 28 16 | Enclosed Switches and Circuit Breakers | 1.5.B.4.a |  | Source Quality Control - Informational | Switches and Circuit Breakers - Source Quality Control Reports | Reports of completed factory testing | Construction
26 28 16 | Enclosed Switches and Circuit Breakers | 1.5.B.6.a |  | Qualifications Statements - Informational | Manufacturer's Qualifications Statements | Manufacturer's qualifications, when requested by Engineer | Construction
26 28 16 | Enclosed Switches and Circuit Breakers | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Switches and Circuit Breakers - Operation and Maintenance Data | O&M manuals and comply with 01 78 23 and recommended spare parts | Closeout
26 28 16 | Enclosed Switches and Circuit Breakers | 1.5.D.1.a |  | Spare Parts - Maintenance Material | Switches and Circuit Breakers - Spare Parts | One set of spare fuses for each fuse disconnect switch to be installed | Construction
26 29 13 | Motor Controllers | 1.5.A.1.a |  | Product Data - Action | Motor Controllers - Product Data | Product schedule for each controller | Construction
26 29 13 | Motor Controllers | 1.5.A.2.a |  | Shop Drawings - Action | Motor Controllers - Shop Drawings | Plans, showing elevations, sections, and mounting details | Construction
26 29 13 | Motor Controllers | 1.5.A.2.b |  | Shop Drawings - Action | Wire Termination Diagrams and Schedules | diagrams for signal and control wiring | Construction
26 29 13 | Motor Controllers | 1.5.B.5.a |  | Field Quality Control - Informational | Visual and Mechanical Inspection Report |  | Construction
26 29 13 | Motor Controllers | 1.5.B.5.b |  | Field Quality Control - Informational | Electrical Test Report |  | Construction
26 29 13 | Motor Controllers | 1.5.B.5.c |  | Field Quality Control - Informational | System Function Test Report |  | Construction
26 29 13 | Motor Controllers | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Motor Controllers Operation and Maintenance Data | Comply with 01 78 23 Operation and Maintenance Data | Closeout
26 29 13 | Motor Controllers | 1.5.C.2.a |  | Record Documentation - Closeout | Motor Controllers - Record Documentation | As stated within the contract documents | Closeout
26 29 13 | Motor Controllers | 1.5.C.4.a |  | Warranty Documentation - Closeout | Motor Controllers - Warranty Documentation | As stated within the contract documents | Closeout
26 29 13 | Motor Controllers | 1.5.D.1.a |  | Spare Parts - Maintenance Material | Motor Controllers - Spare Parts | Furnish spare fuses for fused switches, control power fuses, indicating lights, auxiliary contacts, and power contacts | Construction
26 29 23 | Low Voltage Variable Frequency Drives | 1.5.A.1.a |  | Product Data - Action | Low-Voltage Variable Frequency Drives - Product Data | Manufacturer's technical information, catalog cuts and product literature | Construction
26 29 23 | Low Voltage Variable Frequency Drives | 1.5.A.2.a |  | Shop Drawings - Action | Low-Voltage Variable Frequency Drives - Shop Drawings | Detailed diagrams and dimensional information | Construction
26 29 23 | Low Voltage Variable Frequency Drives | 1.5.B.1.a |  | Certificates - Informational | Low-Voltage Variable Frequency Drives - Certificates | low-voltage variable frequency drive manufacturer and motor manufacturer compatibility certification letters | Construction
26 29 23 | Low Voltage Variable Frequency Drives | 1.5.B.2.a |  | Test and Evaluation Reports - Informational | Low-Voltage Variable Frequency Drives - Testing Plans | Description of shop and field testing measures | Construction
26 29 23 | Low Voltage Variable Frequency Drives | 1.5.B.4.a |  | Source Quality Control - Informational | Low-Voltage Variable Frequency Drives - Source Quality Control | Results of source quality control tests and inspections | Construction
26 29 23 | Low Voltage Variable Frequency Drives | 1.5.B.5.a |  | Field Quality Control - Informational | Low-Voltage Variable Frequency Drives - Field Quality Control | Results of field quality control tests and inspections | Construction
26 29 23 | Low Voltage Variable Frequency Drives | 1.5.B.6.a |  | Qualifications Statements - Informational | Manufacturer Qualifications Statement | When requested by engineer | Construction
26 29 23 | Low Voltage Variable Frequency Drives | 1.5.B.7.a |  | Manufacturer Reports - Informational | Low-Voltage Variable Frequency Drives - Manufacturer Reports | Results of manufacturer site visits | Construction
26 29 23 | Low Voltage Variable Frequency Drives | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Low-Voltage Variable Frequency Drives - Operations and Maintenance Data | Complete installation, operation and maintenance manuals | Closeout
26 29 23 | Low Voltage Variable Frequency Drives | 1.5.C.2.a |  | Record Documentation - Closeout | Low-Voltage Variable Frequency Drives - Record Documentation | Provide record documentation as stated in the contract documents | Closeout
26 29 23 | Low-Voltage Variable Frequency Drives | 1.5.C.3.a |  | Training Material - Informational | Low-Voltage Variable Frequency Drives Training Material | Proposed Training Material; Student Material and Instructor guide. | Closeout
26 29 23 | Low-Voltage Variable Frequency Drives | 1.5.C.3.c |  | Training Instructor(s) resume(s) | Low-Voltage Variable Frequency Drives Resumes | Resumes with references of each instructor for the traning material. | Closeout
26 32 13.13 | Diesel-Engine-Driven Generator Sets | 1.5.A.1.a |  | Product Data - Action | Diesel-Engine-Driven Generator Sets - Product Data | Manufacturer's technical information, catalog cuts and product literature | Construction
26 32 13.13 | Diesel-Engine-Driven Generator Sets | 1.5.A.2.a |  | Shop Drawings - Action | Diesel-Engine-Driven Generator Sets - Shop Drawings | Detailed diagrams and dimensional information | Construction
26 32 13.13 | Diesel-Engine-Driven Generator Sets | 1.5.B.2.a |  | Test and Evaluation Reports - Informational | Diesel-Engine-Driven Generator Sets - Testing Plans | Description of shop and field testing measures | Construction
26 32 13.13 | Diesel-Engine-Driven Generator Sets | 1.5.B.4.a |  | Source Quality Control - Informational | Diesel-Engine-Driven Generator Sets - Source Quality Control | Results of source quality control tests and inspections | Construction
26 32 13.13 | Diesel-Engine-Driven Generator Sets | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Diesel-Engine-Driven Generator Sets - Operations and Maintenance Data | Complete installation, operation and maintenance manuals | Closeout
26 32 13.13 | Diesel-Engine-Driven Generator Sets | 1.5.C.3.a |  | Training Material - Informational | Diesel-Engine-Driven Generator Sets Training Material | Proposed Training Material; Student Material and Instructor guide. | Closeout
26 32 13.13 | Diesel-Engine-Driven Generator Sets | 1.5.C.3.c |  | Training Instructor(s) resume(s) | Diesel-Engine-Driven Generator Sets Resumes | Resumes with references of each instructor for the traning material. | Closeout
26 32 13.13 | Diesel-Engine-Driven Generator Sets | 1.5.D.1.a |  | Spare Parts - Maintenance Material | Diesel-Engine-Driven Generator Sets - Spare Parts | List of spare parts for each size and type to be installed | Construction
26 32 13.16 | Gaseous-Engine-Driven Generator Sets | 1.5.A.1.a |  | Product Data - Action | Gaseous-Engine-Driven Generator Sets - Product Data | Manufacturer's technical information, catalog cuts and product literature | Construction
26 32 13.16 | Gaseous-Engine-Driven Generator Sets | 1.5.A.2.a |  | Shop Drawings - Action | Gaseous-Engine-Driven Generator Sets - Shop Drawings | Detailed diagrams and dimensional information | Construction
26 32 13.16 | Gaseous-Engine-Driven Generator Sets | 1.5.B.2.a |  | Test and Evaluation Reports - Informational | Gaseous-Engine-Driven Generator Sets - Testing Plans | Description of shop and field testing measures | Construction
26 32 13.16 | Gaseous-Engine-Driven Generator Sets | 1.5.B.4.a |  | Source Quality Control - Informational | Gaseous-Engine-Driven Generator Sets - Source Quality Control | Results of source quality control tests and inspections | Construction
26 32 13.16 | Gaseous-Engine-Driven Generator Sets | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Gaseous-Engine-Driven Generator Sets - Operations and Maintenance Data | Complete installation, operation and maintenance manuals | Closeout
26 32 13.16 | Gaseous-Engine-Driven Generator Sets | 1.5.C.3.a |  | Training Material - Informational | Gaseous-Engine-Driven Generator Sets Training Material | Proposed Training Material; Student Material and Instructor guide. | Closeout
26 32 13.16 | Gaseous-Engine-Driven Generator Sets | 1.5.C.3.c |  | Training Instructor(s) resume(s) | Gaseous-Engine-Driven Generator Sets Resumes | Resumes with references of each instructor for the traning material. | Closeout
26 32 13.16 | Gaseous-Engine-Driven Generator Sets | 1.5.D.1.a |  | Spare Parts - Maintenance Material | Gaseous-Engine-Driven Generator Sets - Spare Parts | List of spare parts for each size and type to be installed | Construction
26 36 23 | Automatic Transfer Switches | 1.5.A.1.a |  | Product Data - Action | Automatic Transfer Switches - Product Data | Product data including rated capacities, operating characteristics, electrical characteristics, etc. | Construction
26 36 23 | Automatic Transfer Switches | 1.5.A.2.a |  | Shop Drawings - Action | Automatic Transfer Switches - Shop Drawings | For each type include: dimensions and technical data, charts and related data | Construction
26 36 23 | Automatic Transfer Switches | 1.5.B.1.a |  | Certificates - Informational | Automatic Transfer Switches - Certificates | Manufacturer's UL 1008 certification. | Construction
26 36 23 | Automatic Transfer Switches | 1.5.B.3.a |  | Manufacturers Instructions - Informational | Automatic Transfer Switches - Manufacturers Instructions | Instructions for each type | Construction
26 36 23 | Automatic Transfer Switches | 1.5.B.4.a |  | Source Quality Control - Informational | Automatic Transfer Switches Source Quality Control Reports | Manufacturer's shop testing | Construction
26 36 23 | Automatic Transfer Switches | 1.5.B.6.a |  | Qualifications Statements - Informational | Manufacturer Qualifications Statements | When requested by Engineer | Construction
26 36 23 | Automatic Transfer Switches | 1.5.B.7.a |  | Manufacturer Reports - Informational | Automatic Transfer Switches Manufacturer Report | written report of results of each visit to Site by Supplier’s service technician | Construction
26 36 23 | Automatic Transfer Switches | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Automatic Transfer Switches - Operations and Maintenance Data | Complete installation, operation and maintenance manuals | Closeout
26 36 23 | Automatic Transfer Switches | 1.5.C.2.a |  | Record Documentation - Closeout | Automatic Transfer Switches - Record Documentation | Provide record documentation as stated in the contract documents | Closeout
26 36 23 | Automatic Transfer Switches | 1.5.C.3.a |  | Training Material - Informational | Automatic Transfer Switches Training Material | Proposed Training Material; Student Material and Instructor guide. | Closeout
26 36 23 | Automatic Transfer Switches | 1.5.C.3.c |  | Training Instructor(s) resume(s) | Automatic Transfer Switches Resumes | Resumes with references of each instructor for the traning material. | Closeout
26 36 23 | Automatic Transfer Switches | 1.5.C.4.a |  | Warranty Documentation - Closeout | Automatic Transfer Switches - Warranty Documentation | Manufacturer's warranty | Closeout
26 43 13 | Surge Protective Devices | 1.5.A.1.a |  | Product Data - Action | Surge Protective Devices - Product Data | Product data including rated capacities, operating characteristics, electrical characteristics, etc. | Construction
26 43 13 | Surge Protective Devices | 1.5.B.2.a |  | Test and Evaluation Reports - Informational | Surge Protective Devices - Test and Evaluation Reports | Copy of UL category code VZCA certification, listing testing values for VPRs, Inomial ratings, etc. | Construction
26 43 13 | Surge Protective Devices | 1.5.B.3.a |  | Manufacturers Instructions - Informational | Surge Protective Devices - Manufacturers Instructions | Instructions for each type | Construction
26 43 13 | Surge Protective Devices | 1.5.B.5.a |  | Field Quality Control - Informational | Surge Protective Devices - Field Quality Control | Results of field quality control reports | Construction
26 43 13 | Surge Protective Devices | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Surge Protective Devices - Operations and Maintenance Data | Complete installation, operation and maintenance manuals | Closeout
26 43 13 | Surge Protective Devices | 1.5.C.3.a |  | Training Material - Informational | Surge Protective Devices Training Material | Proposed Training Material; Student Material and Instructor guide. | Closeout
26 43 13 | Surge Protective Devices | 1.5.C.3.c |  | Training Instructor(s) resume(s) | Surge Protective Devices Resumes | Resumes with references of each instructor for the traning material. | Closeout
26 43 13 | Surge Protective Devices | 1.5.C.4.a |  | Warranty Documentation - Closeout | Surge Protective Devices - Warranty Documentation | Manufacturer's warranty | Closeout
26 51 00 | Interior Lighting | 1.5.A.1.a |  | Product Data - Action | Interior Lighting - Product Data | Manufacturer's technical information | Construction
26 51 00 | Interior Lighting | 1.5.A.2.a |  | Shop Drawings - Action | Interior Lighting - Shop Drawings | Detailed nonstandard fixtures, dimensions, weights, method of field assembly, components, features and accessories | Construction
26 51 00 | Interior Lighting | 1.5.B.5.a |  | Field Quality Control - Informational | Interior Lighting - Field Quality Control Reports | Results of required field quality control test and inspections | Construction
26 51 00 | Interior Lighting | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Interior Lighting – Operation and Maintenance Data | Maintenance data for fixtures | Closeout
26 51 00 | Interior Lighting | 1.5.D.2.a |  | Extra Stock Materials - Maintenance Material | Interior Lighting - Extra Stock Materials | Extra materials descriptions and packaging contents | Construction
26 56 00 | Exterior Lighting | 1.5.A.1.a |  | Product Data - Action | Exterior Lighting - Product Data | Specifications, cut sheets, dimensions and technical data. | Construction
26 56 00 | Exterior Lighting | 1.5.A.2.a |  | Shop Drawings - Action | Nonstandard Fixtures and Poles Shop Drawings | Dimensions, weights, method of assembly, components, and accessories | Construction
26 56 00 | Exterior Lighting | 1.5.A.2.b |  | Shop Drawings - Action | Wiring Diagrams | Detailed wiring for control system | Construction
26 56 00 | Exterior Lighting | 1.5.A.2.c |  | Shop Drawings - Action | Anchor-Bolt Templates | Keyed to specific poles and certified by the manufacturer | Construction
26 56 00 | Exterior Lighting | 1.5.B.5.a |  | Field Quality Control - Informational | Exterior Lighting – Field Quality Control Reports | Results of required field quality control test and inspections | Construction
26 56 00 | Exterior Lighting | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Exterior Lighting Operating and Maintenance Data | Maintenance data for fixtures | Closeout
26 56 00 | Exterior Lighting | 1.5.D.2.a |  | Extra Stock Materials - Maintenance Material | Exterior Lighting Extra Materials | Extra materials that match products installed | Construction
Division 27 - Communications
27 00 00 | Communications | 1.5.A.1.a |  | Product Data - Action | Communications - Product Data | Manufacturer literature and standard catalogue data. Description of construction features. Dimensions and weights. | Construction
27 00 00 | Communications | 1.5.A.2.a |  | Shop Drawings - Action | Communication Network Layout Drawings | Drawings of proposed layout of communication network and communications, showing related equipment in relation to each other. | Construction
27 00 00 | Communications | 1.5.B.2.a |  | Test and Evaluation Reports - Informational | Communications - Test and Evaluation Reports | Factory Test reports and installation inspection reports | Construction
27 00 00 | Communications | 1.5.B.3.a |  | Manufacturers Instructions - Informational | Manufacturers' Instructions for Installation and Mounting | Installation and mounting details, instructions, and recommendations. Service requirements | Construction
27 00 00 | Communications | 1.5.B.5.a |  | Field Quality Control - Informational | Communications - Field Quality Control Reports | Results of required Field Quality Control tests and inspections. | Construction
27 00 00 | Communications | 1.5.B.6.a |  | Qualifications Statements - Informational | Installer Qualifications | Provide Installer qualifications and information in accordance with this Section. | Construction
27 00 00 | Communications | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Operation and Maintenance Manuals for Communication Components | In accordance with 01 78 23 Operation and Maintenance Data | Closeout
27 00 00 | Communications | 1.5.C.2.a |  | Record Documentation - Closeout | Project Record Documents | Detailed records reflecting installed conditions | Closeout
27 05 53 | Identification For Communication Systems | 1.5.A.1.a |  | Product Data - Action | Identification for Communications Systems – Product Data | Manufacturer’s literature, cut sheets, specifications, dimensions and technical data for all products proposed under this Section. | Construction
27 05 53 | Identification For Communication Systems | 1.5.A.2.a |  | Shop Drawings - Action | Communication Systems - Drawings | Complete description and listing of proposed electrical identification and electrical identification devices for associated equipment or systems. | Construction
27 05 53 | Identification For Communication Systems | 1.5.A.3.a |  | Samples - Action | Communication Systems - Samples | For each type of label and sign to illustrate size, colors, lettering style, mounting provisions, and graphic features of identification products. | Construction
27 05 53 | Identification For Communication Systems | 1.5.C.2.a |  | Record Documentation - Closeout | Identification For Communication Systems - Schedule | An index of nomenclature of electrical equipment and system components used in identification signs and labels. | Closeout
27 11 16 | Communication Enclosures | 1.5.A.1.a |  | Product Data - Action | Communications Enclosures – Product Data | Manufacturer's product data sheets and complete construction details | Construction
27 11 16 | Communication Enclosures | 1.5.A.2.a |  | Shop Drawings - Action | Communications Layout Drawings | Layout drawings showing routing of cables, termination and equipment locations, and bill of materials for each termination location | Construction
27 11 16 | Communication Enclosures | 1.5.B.3.a |  | Manufacturers Instructions - Informational | Installation Instructions | Manufacturer’s installation instructions, procedures and specific tools. | Construction
27 13 24 | Fiber Optic Cable and Appurtenances | 1.5.A.1.a |  | Product Data - Action | Fiber Optic Cable and Appurtenances – Product Data | Manufacturer's product data sheets and complete construction details including physical characteristics of optical fiber, strength members, and jackets. | Construction
27 13 24 | Fiber Optic Cable and Appurtenances | 1.5.A.2.a |  | Shop Drawings - Action | Fiber Optic Cable Pulling Plan | Specify the sequence of work tasks, materials, and equipment. | Construction
27 13 24 | Fiber Optic Cable and Appurtenances | 1.5.A.2.b |  | Shop Drawings - Action | Fiber Optic Cable Layout Drawings | Show routing of cables, termination and equipment locations and bill of materials for each termination location. | Construction
27 13 24 | Fiber Optic Cable and Appurtenances | 1.5.A.2.c |  | Shop Drawings - Action | Fiber Optic Cable Design Data | Design drawings and link design | Construction
27 13 24 | Fiber Optic Cable and Appurtenances | 1.5.B.2.a |  | Test and Evaluation Reports - Informational | Fiber Optic Cable Production Test Reports | Cable manufacturer's certified test data for attenuation and bandwidth and the maximum pulling strain allowed. | Construction
27 13 24 | Fiber Optic Cable and Appurtenances | 1.5.B.2.b |  | Test and Evaluation Reports - Informational | Test Instruments Certifications | Power meters shall have calibrations traceable to National Institute of Standards and Technology (NIST) standards. | Construction
27 13 24 | Fiber Optic Cable and Appurtenances | 1.5.B.3.a |  | Manufacturers Instructions - Informational | Installation Instructions | Manufacturer’s installation instructions, procedures and specific tools. | Construction
27 13 24 | Fiber Optic Cable and Appurtenances | 1.5.B.5.a |  | Field Quality Control - Informational | Fiber Optic Cable – Field Quality Control Reports | Contractor shall submit certified field reports | Construction
27 13 24 | Fiber Optic Cable and Appurtenances | 1.5.B.6.a |  | Qualifications Statements - Informational | Fiber Optic Qualifications Statements | Installer and personnel qualifications | Construction
27 15 13 | Copper Cable For Communication and Appurtenances | 1.5.A.1.a |  | Product Data - Action | Copper Cable and Appurtenances – Product Data | Manufacturer’s literature, cut sheets, specifications, dimensions and technical data for all products proposed under this Section. | Construction
27 15 13 | Copper Cable For Communication and Appurtenances | 1.5.A.2.a |  | Shop Drawings - Action | Copper Cable Pulling Plan | Specify the sequence of work tasks, materials, and equipment. | Construction
27 15 13 | Copper Cable For Communication and Appurtenances | 1.5.A.2.b |  | Shop Drawings - Action | Copper Cable Layout Drawings | Show routing of cables, termination and equipment locations and bill of materials for each termination location. | Construction
27 15 13 | Copper Cable For Communication and Appurtenances | 1.5.B.2.a |  | Test and Evaluation Reports - Informational | Copper Cable Production Test Reports | Cable manufacturer's certified test data for attenuation and bandwidth and the maximum pulling strain allowed. | Construction
27 15 13 | Copper Cable For Communication and Appurtenances | 1.5.B.2.b |  | Test and Evaluation Reports - Informational | Test Instruments Certifications | Power meters shall have calibrations traceable to National Institute of Standards and Technology (NIST) standards. | Construction
27 15 13 | Copper Cable For Communication and Appurtenances | 1.5.B.3.a |  | Manufacturers Instructions - Informational | Installation Instructions | Manufacturer’s installation instructions, procedures and specific tools. | Construction
27 15 13 | Copper Cable For Communication and Appurtenances | 1.5.B.5.a |  | Field Quality Control - Informational | Copper Cable Field Quality Control Reports | Contractor shall submit certified field reports | Construction
27 15 13 | Copper Cable For Communication and Appurtenances | 1.5.B.6.a |  | Qualifications Statements - Informational | Copper Cable Qualifications Statements | Installer and personnel qualifications | Construction
Division 31 - Earthwork
31 00 05 | Trenching and Earthwork | 1.5.A.1.a |  | Product Data - Action | Material Sources and Gradations | Submit source of materials, and when gradation is specified, submit gradation test for each type of material specified. | Construction
31 00 05 | Trenching and Earthwork | 1.5.A.2.a |  | Shop Drawings - Action | Final Surveyed Grades | Upon completion of grading for grade dependent earthwork, submit final surveyed grades. | Construction
31 00 05 | Trenching and Earthwork | 1.5.A.3.a |  | Samples - Action | Samples of Earthwork Products | Samples of products including geotextiles, fill, gravel and base materials | Construction
31 00 05 | Trenching and Earthwork | 1.5.A.4.a |  | Delegated Design - Action | Excavation and Trench Protection and Dewatering Systems | Include design provisions for Dewatering System, trench sheeting and bracing, cofferdam system, and underpinning. | Construction
31 00 05 | Trenching and Earthwork | 1.5.B.5.a | 1.5.B.5.a.1. | Field Quality Control - Informational | Borrow Material Tests | Submit a monthly test report | Construction
31 00 05 | Trenching and Earthwork | 1.5.B.5.b | 1.5.B.5.b.1. | Field Quality Control - Informational | Excavation Subgrade Tests | Submit a monthly test report including footers | Construction
31 00 05 | Trenching and Earthwork | 1.5.B.5.c | 1.5.B.5.c.1. | Field Quality Control - Informational | Field Density Tests | Submit a monthly test report | Construction
31 00 05 | Trenching and Earthwork | 1.5.B.5.d | 1.5.B.5.d.1. | Field Quality Control - Informational | Optimum Moisture- Backfill Materials | Submit a monthly test report of maximum density curve for each soil used for backfill. | Construction
31 00 05 | Trenching and Earthwork | 1.5.B.5.e | 1.5.B.5.e.1. | Field Quality Control - Informational | Unconfined Compressive Strength Tests/ Bearing Tests | Submit a monthly test report of each strata. | Construction
31 00 05 | Trenching and Earthwork | 1.5.B.5.f | 1.5.B.5.f.1. | Field Quality Control - Informational | Flowable Fill Tests | Submit compressive strength test report. | Construction
31 00 05 | Trenching and Earthwork | 1.5.B.5.g |  | Field Quality Control - Informational | Compaction Procedures and Equipment | Submit the proposed compaction procedure and equipment to be used | Construction
31 00 05 | Trenching and Earthwork | 1.5.B.5.h |  | Field Quality Control - Informational | Sheet Shoring and Bracing Procedure and Equipment | Submit the proposed sheet shoring and bracing procedure and equipment to be used. | Construction
31 00 05 | Trenching and Earthwork | 1.5.B.5.i |  | Field Quality Control - Informational | Additional Field Testing Reports | As specified in Part 3 of the specification. | Construction
31 00 05 | Trenching and Earthwork | 1.5.B.6.a |  | Qualifications Statements - Informational | Earthwork Testing Agency Qualifications | Submit qualifications for earthwork testing agency. | Construction
31 05 19 | Geosynthetics for Earthwork | 1.5.A.1.a |  | Product Data - Action | Geosynthetics Manufacturer's Product Data | Manufacturer's Product Data, including product material properties and installation requirements. | Construction
31 05 19 | Geosynthetics for Earthwork | 1.5.B.1.a |  | Certificates - Informational | Geosynthetics Compliance Certificate | Submit an information certifying that the filter fabric furnished complies with all requirements specified herein | Construction
31 11 00 | Clearing and Grubbing | 1.5.A.2.a |  | Shop Drawings - Action | Tree and Vegetation Removal Plan | Submit as required, plan only needed if removal differs from Contract Drawings | Construction
31 11 00 | Clearing and Grubbing | 1.5.A.2.b |  | Shop Drawings - Action | Clearing and Grubbing Limits | Submit as required, plan only needed if clearing and grubbing limits differs from Contract Drawings | Construction
31 32 20 | Channel Protection Systems | 1.5.A.1.a |  | Product Data - Action | Channel Protection Systems – Product Data | Submit channel protection system manufacturer's data, installation instructions, and dimensions. | Construction
31 32 20 | Channel Protection Systems | 1.5.A.2.a |  | Shop Drawings - Action | Channel Protection Systems – Manufacturer's Shop Drawings | Submit Manufacturer’s shop drawings and section layout for channel protection system. | Construction
31 32 20 | Channel Protection Systems | 1.5.A.3.a |  | Samples - Action | Channel Protection Systems – Samples | Submit Manufacturer’s product samples | Construction
31 32 20 | Channel Protection Systems | 1.5.B.1.a |  | Certificates - Informational | Manufacturers' Certificate of Compliance with Standards | As requested, submit Manufacturer’s certification of compliance to all applicable testing procedures and related specifications. | Construction
31 32 20 | Channel Protection Systems | 1.5.B.6.a |  | Qualifications Statements - Informational | Installer and Field Representative Qualifications | Certifying the installer and field representative is experienced in the installation of the specified products. | Construction
31 32 20 | Channel Protection Systems | 1.5.C.4.a |  | Warranty Documentation - Closeout | Channel Protection Systems Warranty | Written warranty, signed by Contractor and installer, as specified. | Closeout
31 32 21 | Vegetated Coir Logs | 1.5.A.1.a |  | Product Data - Action | Vegetated Coir Logs- Product Data | Provide Manufacturer’s and Supplier’s vegetated coir logs product data. | Construction
31 32 21 | Vegetated Coir Logs | 1.5.A.2.a |  | Shop Drawings - Action | Vegetated Coir Logs – Shop Drawings | Submit Vegetated Coir Log installation schedule indicating order date and anticipated dates and locations for each type of activity. | Construction
31 32 21 | Vegetated Coir Logs | 1.5.B.1.a |  | Certificates - Informational | Manufacturer's Certificates | Certification by manufacturer or vendor that the products supplied comply with Vegetated Coir Log requirements | Construction
31 32 21 | Vegetated Coir Logs | 1.5.B.6.a |  | Qualifications Statements - Informational | Manufacturer's Qualifications | Manufacturer and installer qualification data specified to demonstrate their capabilities and experience. Include lists of completed projects with project names and addresses, names and address of architects and owners, and other information specified. | Construction
31 32 21 | Vegetated Coir Logs | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Vegetated Coir Logs – Operation and Maintenance Data | Maintenance Instructions: Manufacturer’s recommended procedures established by Owner for maintenance of exterior plants during a calendar year. | Closeout
31 32 21 | Vegetated Coir Logs | 1.5.C.4.a |  | Warranty Documentation - Closeout | Vegetated Coir Logs Warranty Documentation | Submit written warranty, signed by Contractor and landscape installer, as specified. | Closeout
31 36 10 | Gabions and Revetment Mattresses | 1.5.A.1.a |  | Product Data - Action | Gabion and Revetment Mattresses Product Data | Manufacturer's Product Data, including product material properties and installation requirements. Stone fill type and gradation. | Construction
Division 32 - Exterior Improvements
32 05 19.19 | Geogrids For Exterior Improvements | 1.5.A.1.a |  | Product Data - Action | Geogrids for Exterior Improvements Product Data | Manufacturer's Product Data, including product material properties and installation requirements. | Construction
32 05 19.19 | Geogrids For Exterior Improvements | 1.5.A.2.a |  | Shop Drawings - Action | Manufacturer's Shop Drawings- Section Layout | Submit Manufacturer’s shop drawings and section layout for surface protection system. | Construction
32 05 19.19 | Geogrids For Exterior Improvements | 1.5.A.3.a |  | Samples - Action | Geogrids for Exterior Improvements - Samples | Submit Manufacturer’s product samples | Construction
32 05 19.19 | Geogrids For Exterior Improvements | 1.5.B.1.a |  | Certificates - Informational | Manufacturers' Certificate of Compliance with Standards | Manufacturer’s certification of compliance to all applicable testing procedures and related specifications | Construction
32 05 19.19 | Geogrids For Exterior Improvements | 1.5.B.1.b |  | Certificates - Informational | Manufacturer’s Certification of Polyethylene Used to Make Cellular Confinement System | Manufacturer's Certification of percentage carbon black. Resin manufacturer's certification of polyethylene density and ESCR | Construction
32 05 19.19 | Geogrids For Exterior Improvements | 1.5.B.6.a |  | Qualifications Statements - Informational | Installer and Field Representative Qualifications | Certifying the installer and field representative is experienced in the installation of the specified products. | Construction
32 05 19.19 | Geogrids For Exterior Improvements | 1.5.C.4.a |  | Warranty Documentation - Closeout | Geogrids for Exterior Improvements - Warranty Documentation | Written warranty, signed by Contractor and installer, as specified. | Closeout
32 12 16 | Asphalt Paving | 1.5.A.1.a |  | Product Data - Action | Job Mix Design | Detailed product data on each asphalt mix design | Construction
32 12 16 | Asphalt Paving | 1.5.B.1.a |  | Certificates - Informational | INDOT Certified Asphalt Producer | INDOT list of certified hot mix asphalt producers, dated within the last 12 months and highlight the plant name and certification number | Construction
32 12 16 | Asphalt Paving | 1.5.B.1.b |  | Certificates - Informational | INDOT Certified HMA Mix Design | INDOT list of approved HMA mix design laboratories, dated within the last 12 months and highlight the laboratory name and certification number | Construction
32 13 00 | Rigid Paving | 1.5.A.1.a |  | Product Data - Action | INDOT Concrete Mix Design Spreadsheet | INDOT Material and Test Division standard form “INDOT Concrete Mix Design Spreadsheet for English Contracts” | Construction
32 13 00 | Rigid Paving | 1.5.B.1.a |  | Certificates - Informational | INDOT Concrete Mix Design Certificates | Certificates, signed by the materials producer and the paving Subcontractor, stating that materials meet or exceed the specified requirements | Construction
32 13 43 | Pervious Rigid Paving | 1.5.A.1.a |  | Product Data - Action | Pervious Rigid Paving - Product Data | Product data on the mix design of the paving product. | Construction
32 13 43 | Pervious Rigid Paving | 1.5.A.2.a |  | Shop Drawings - Action | Joint Layout Drawings | Proposed joint locations, shown on Drawings. | Construction
32 13 43 | Pervious Rigid Paving | 1.5.A.3.a |  | Samples - Action | Color Selection Products | Samples of the concrete products that required color selection. | Construction
32 13 43 | Pervious Rigid Paving | 1.5.B.2.a |  | Test and Evaluation Reports - Informational | Past Installation Test Results | In-place pavement test results from the last 12 months. | Construction
32 13 43 | Pervious Rigid Paving | 1.5.B.2.b |  | Test and Evaluation Reports - Informational | Test Panels | Test Panel Reports as described in ACI 522.1-08 | Construction
32 13 43 | Pervious Rigid Paving | 1.5.B.6.a |  | Qualifications Statements - Informational | Manufacturers' Qualifications | Qualifications of Contractor related to construction of pervious concrete pavements. | Construction
32 13 43 | Pervious Rigid Paving | 1.5.B.6.b |  | Qualifications Statements - Informational | Testing Agency Qualifications | Include test and inspection results | Construction
32 90 00 | Planting | 1.5.A.1.a |  | Product Data - Action | Planting - Product Data | Manufacturer's product data and specifications for all required materials. | Construction
32 90 00 | Planting | 1.5.A.2.a |  | Shop Drawings - Action | Planting - Schedule | Indicating anticipated planting dates for each type of planting | Construction
32 90 00 | Planting | 1.5.A.2.b |  | Shop Drawings - Action | Final Seedbed Preparation | Submit method of tillage for final seedbed preparation. Disking or rototilling to cover the site at least twice is the preferred method | Construction
32 90 00 | Planting | 1.5.B.1.a |  | Certificates - Informational | Planting - Certificates | Certificates required by law to accompany shipments. | Construction
32 90 00 | Planting | 1.5.B.3.a |  | Manufacturers Instructions - Informational | Planting - Manufacturers' Instructions | Manufacturer’s installation instructions for all required materials | Construction
32 90 00 | Planting | 1.5.B.4.a |  | Source Quality Control - Informational | Planting - Source Quality Control Data | Written statement providing the locations of the property from which the plantings are to be obtained and the names and addresses of the suppliers. | Construction
32 90 00 | Planting | 1.5.B.9.a |  | Special Procedures - Informational | Planting - Schedule of Values | Schedule of values including appropriate breakdown of materials intended to be installed for all plantings. | Construction
32 90 00 | Planting | 1.5.C.2.a |  | Record Documentation - Closeout | Planting - Record Documentation | Submit as built plan upon project completion including location of planting areas and species and quantities planted. | Closeout
32 90 00 | Planting | 1.5.C.4.a |  | Warranty Documentation - Closeout | Planting - Warranty Documentation | Submit written warranty, signed by Contractor and landscape installer, as specified. | Closeout
32 92 00 | Lawns and Grasses | 1.5.A.1.a |  | Product Data - Action | Lawns and Grasses - Product Data | Fertilizer composition analysis. Hydroseed mixture proportions, product data, and water requirements. Seed product data including bulk weight of seed to equal 1 lb. of 100% pure germinated seed. | Construction
32 92 00 | Lawns and Grasses | 1.5.B.1.a |  | Certificates - Informational | Top Soil Certification | Manufacturer's qualified testing agency's certified analysis of top soil products | Construction
32 92 00 | Lawns and Grasses | 1.5.B.1.b |  | Certificates - Informational | Seed Supplier Certification | Supplier certification of seed and storage requirements. | Construction
32 92 00 | Lawns and Grasses | 1.5.B.4.a |  | Source Quality Control - Informational | Sod Supply Information | Written statement providing locations of the property from where the sod is obtained. Including names and address. | Construction
32 92 00 | Lawns and Grasses | 1.5.B.4.b |  | Source Quality Control - Informational | Seed Packaging Information | Certification that seed has been stored in compliance with recommendation of the seed supplier | Construction
Division 33 - Utilities
33 01 30.53 | Spray Applied Sewer Rehabilitation | 1.5.A.1.a |  | Product Data - Action | Spray Applied Product Data | Manufacturer's product data, installation instructions, substrate preparation, and on-site quality assurance | Construction
33 01 30.53 | Spray Applied Sewer Rehabilitation | 1.5.A.2.a |  | Shop Drawings - Action | Liner Thickness Calculations | Liner Thickness Calculations– Engineer shall be notified if Contractor’s calculations show a thicker liner needed than specified in the project manual. | Construction
33 01 30.53 | Spray Applied Sewer Rehabilitation | 1.5.B.2.a |  | Test and Evaluation Reports - Informational | Testing Laboratory and Procedures | Testing Laboratory and Proposed Testing Procedures | Construction
33 01 30.53 | Spray Applied Sewer Rehabilitation | 1.5.B.6 |  | Qualifications Statements - Informational | Liner Product Qualification Statements | Liners shall come from a manufacturer with at least 5 years’ experience producing CIPP liners with satisfactory results. | Construction
33 01 30.53 | Spray Applied Sewer Rehabilitation | 1.5.B.9.a |  | Special Procedures - Informational | Bypass Pumping Plan | Bypass Pumping Plan | Construction
33 01 30.53 | Spray Applied Sewer Rehabilitation | 1.5.B.9.b |  | Special Procedures - Informational | Pre-Installation Internal Pipe Televising Tabular Sheets | Pre-Installation Internal Pipe Televising Tabular Sheets (with videos submitted separately) | Construction
33 01 30.53 | Spray Applied Sewer Rehabilitation | 1.5.B.9.c |  | Special Procedures - Informational | Post-Installation Internal Pipe Televising Tabular Sheets | Post-Installation Internal Pipe Televising Tabular Sheets (with videos submitted separately) | Construction
33 01 30.53 | Spray Applied Sewer Rehabilitation | 1.5.B.9.d |  | Special Procedures - Informational | Sewer Cleaning Costs (Without Lining) | Sewer Cleaning Costs (Without Lining) - Separated by Pipe Diameter | Construction
33 01 30.53 | Spray Applied Sewer Rehabilitation | 1.5.C.2.a |  | Record Documentation - Closeout | Test Reports | Testing Reports of samples. All samples shall have manhole ID numbers and pipe size associated with each sample. | Closeout
33 01 30.53 | Spray Applied Sewer Rehabilitation | 1.5.C.2.b. |  | Record Documentation - Closeout | List of Lined and Un-Lineable Segments | Final List of Lined and Un-Lineable Segments – PDF submitted through PMIS and Excel Version sent digitally. | Closeout
33 01 30.53 | Spray Applied Sewer Rehabilitation | 1.5.C.4.a |  | Record Documentation - Closeout | Warranty Certificate | Warranty Certificate | Closeout
33 01 30.73 | Pipe Rehabilitation by Cured In Place Pipe Lining | 1.5.A.1.a |  | Product Data - Action | CIPP Product Data | ASTM Compliance, Liner QC Tests, Felt Tube Liner Physical Data, Resin Test Results, and Resin Physical Data | Construction
33 01 30.73 | Pipe Rehabilitation by Cured In Place Pipe Lining | 1.5.A.2.a |  | Shop Drawings - Action | CIPP Liner Thickness Calculations | CIPP Shop Drawings - Liner Thickness Calculations | Construction
33 01 30.73 | Pipe Rehabilitation by Cured In Place Pipe Lining | 1.5.B.2.a |  | Test and Evaluation Reports - Informational | Testing Laboratory and Procedures | Testing Laboratory and Proposed Testing Procedures | Construction
33 01 30.73 | Pipe Rehabilitation by Cured In Place Pipe Lining | 1.5.B.6.a |  | Qualifications Statements - Informational | Liner Product Qualification Statements | Qualifications Statements of Manufacturer | Construction
33 01 30.73 | Pipe Rehabilitation by Cured In Place Pipe Lining | 1.5.B.9.a |  | Special Procedures - Informational | Bypass Pumping Plan | Bypass Pumping Plan | Construction
33 01 30.73 | Pipe Rehabilitation by Cured In Place Pipe Lining | 1.5.B.9.b |  | Special Procedures - Informational | Customer Notification Plan | Customer Notification Plan | Construction
33 01 30.73 | Pipe Rehabilitation by Cured In Place Pipe Lining | 1.5.B.9.c |  | Special Procedures - Informational | Pre-Installation Internal Pipe Televising Tabular Sheets | Pre-Installation Internal Pipe Televising Tabular Sheets | Construction
33 01 30.73 | Pipe Rehabilitation by Cured In Place Pipe Lining | 1.5.B.9.d |  | Special Procedures - Informational | Post-Installation Internal Pipe Televising Tabular Sheets | Post-Installation Internal Pipe Televising Tabular Sheets | Construction
33 01 30.73 | Pipe Rehabilitation by Cured In Place Pipe Lining | 1.5.B.9.e |  | Special Procedures - Informational | Sewer Cleaning Costs (Without Lining) | Sewer Cleaning Costs (Without Lining) - Separated by Pipe Diameter | Preconstruction
33 01 30.73 | Pipe Rehabilitation by Cured In Place Pipe Lining | 1.5.C.2.a |  | Record Documentation - Closeout | Test Reports of CIPP Samples | Testing Reports of CIPP Samples | Closeout
33 01 30.73 | Pipe Rehabilitation by Cured In Place Pipe Lining | 1.5.C.2.b |  | Record Documentation - Closeout | List of Lined and Un-Lineable Segments | Final List of Lined and Un-Lineable Segments | Closeout
33 01 30.73 | Pipe Rehabilitation by Cured In Place Pipe Lining | 1.5.C.2.c |  | Record Documentation - Closeout | Temperature Sensor Reports | Temperature Sensor Reports (all pipes greater than 36") | Closeout
33 01 30.74 | Pipe Repair and Replace by Open Excavation | 1.5.B.5.a |  | Field Quality Control - Informational | Pre-Repair Internal Pipe Televising Videos | Video to the Engineer and provide any additional notes | Construction
33 01 30.74 | Pipe Repair and Replace by Open Excavation | 1.5.B.5.b |  | Field Quality Control - Informational | Post-Repair Internal Pipe Televising Videos | Two copies of the post repair video | Construction
33 01 30.74 | Pipe Repair and Replace by Open Excavation | 1.5.B.9.a |  | Special Procedures - Informational | Bypass Pumping Plans | Plans for any areas that will need bypass pumping, including engineering recommendations | Construction
33 01 30.78 | Rehabilitation of Sewer Manholes | 1.5.A.1.a |  | Product Data - Action | Sewer Manholes Rehabilitation - Product Data | Material type and manufacturer to be used, including catalog data showing manufacturer’s clarifications and updates, ASTM references, material composition, specifications, physical properties and chemical resistance, manufacturer’s recommended mix, additives and set time. | Construction
33 01 30.78 | Rehabilitation of Sewer Manholes | 1.5.B.1.a |  | Certificates - Informational | Sanitary Manhole Rehabilitation - Certificates | Certification that backup equipment is available for project within 24hrs and Certification from Manufacturer that contractor is an approved installer of their product. | Construction
33 01 30.78 | Rehabilitation of Sewer Manholes | 1.5.C.2.a |  | Record Documentation - Closeout | Sanitary Sewer Manholes Rehabilitation - Installation Record | Field inspection notes of manholes rehabilitated, quantities and post rehabilitation inspection.Post-Installation photos to be included within this submittal showing all work complete. Multiple photos may be needed for each structure if work is being completed on multiple areas of the structure. | Closeout
33 01 30.78 | Rehabilitation of Sewer Manholes | 1.5.C.4.a |  | Warranty Documentation - Closeout | Sanitary Sewer Manholes Rehabilitation - Warranty Documentation | 3 - year Warranty | Closeout
33 05 13.29 | Fiberglass Manholes and Structures | 1.5.A.1.a |  | Product Data - Action | Fiberglass Manholes and Structures - Product Data | Materials, properties, strengths, coatings, warranties | Construction
33 05 13.29 | Fiberglass Manholes and Structures | 1.5.A.2.a |  | Shop Drawings - Action | Fiberglass Manholes and Structures - Shop Drawings | Drawings of each manhole structure, including thickness, joint length, fitting location, material properties and pressure ratings. | Construction
33 05 13.29 | Fiberglass Manholes and Structures | 1.5.A.4.a |  | Delegated Design - Action | Manhole Design Information | Calculations and design for wall thickness and joint types. Calculations and design for anti-floatation restraints. | Construction
33 05 13.29 | Fiberglass Manholes and Structures | 1.5.B.1.a |  | Certificates - Informational | Manufacturers' Certificate of Compliance with Standards | Manufacturer's Certificate | Construction
33 05 13.29 | Fiberglass Manholes and Structures | 1.5.B.4.a |  | Source Quality Control - Informational | Fiberglass Manholes and Structures - Source Quality Control | Manufacturer's Testing Results | Construction
33 05 13.29 | Fiberglass Manholes and Structures | 1.5.B.6.a |  | Qualifications Statements - Informational | Manufacturers' Qualifications | Minimum of 5 years experience | Construction
33 05 23.13 | Utility Horizontal Directional Drilling | 1.5.A.1.a |  | Product Data - Action | Drilling Fluid Product Data | Manufacturer's product data for drilling fluids. | Construction
33 05 23.13 | Utility Horizontal Directional Drilling | 1.5.A.2.a |  | Shop Drawings - Action | Horizontal Directional Drilling Plan | Plans describing the equipment, methods and monitoring procedures , construction sequence and scheduling, contingency plans | Construction
33 05 23.13 | Utility Horizontal Directional Drilling | 1.5.B.6.a |  | Qualifications Statements - Informational | References | A list of references of persons or firms who can attest to the quality of performed work. | Construction
33 05 23.16 | Utility Pipe Jacking | 1.5.A.2.a |  | Shop Drawings - Action | Utility Pipe Jacking - Installation Plan | Utility Pipe Jacking Installation Plan, including description of work, layout of jacking and receiving pits, material laydown areas and dewatering plan. | Construction
33 05 23.16 | Utility Pipe Jacking | 1.5.B.6.a |  | Qualifications Statements - Informational | Installer Example Projects, Qualifications and References | Example projects, similar to proposed projects, and qualifications of key personnel. Submit as requested, list of installer references. | Construction
33 05 33 | Ductile Iron Pressure Utility Piping | 1.5.A.1.a |  | Product Data - Action | Ductile Iron Pipe and Appurtenances - Product Data | Product data for pipe, fittings, gaskets, appurtenances, linings, and coatings. | Construction
33 05 33 | Ductile Iron Pressure Utility Piping | 1.5.A.1.b |  | Product Data - Action | Ductile Iron Pipe and Appurtenances - Non-Standard Lining and Coating | Surface preparation and application reports and procedures as required for lining and coating of pipe and fittings. | Construction
33 05 33 | Ductile Iron Pressure Utility Piping | 1.5.A.3.a |  | Samples - Action | Samples of Pipe and Fitting of Lining | Submit sample of pipe and fitting with each type of lining for use at the Site to verify continuity via visual inspection | Construction
33 05 33 | Ductile Iron Pressure Utility Piping | 1.5.B.1.a |  | Certificates - Informational | Compliance Standards Certificates | Submit manufacturer's Certificates of compliance | Construction
33 05 33 | Ductile Iron Pressure Utility Piping | 1.5.B.4.a |  | Source Quality Control - Informational | Ductile Iron Pipe - Source Quality Control Reports | Reports of completed factory testing. When requested by Engineer submit lining and coating test coupons. | Construction
33 05 33.13 | Ductile Iron Non-Pressure Utility Piping | 1.5.A.1.a |  | Product Data - Action | Ductile Iron Pipe and Appurtenances - Product Data | Product data for pipe, fittings, gaskets, linings, coatings, and appurtenances. | Construction
33 05 33.13 | Ductile Iron Non-Pressure Utility Piping | 1.5.A.1.b |  | Product Data - Action | Ductile Iron Pipe and Appurtenances Non-Standard Lining and Coating | Submit as required, surface preparation and application reports and procedures for lining and coating of pipes and fittings. | Construction
33 05 33.13 | Ductile Iron Non-Pressure Utility Piping | 1.5.A.3.a |  | Samples - Action | Samples of Pipe and Fitting of Lining | Submit as required, surface preparation and application reports and procedures for lining and coating of pipes and fittings. | Construction
33 05 33.13 | Ductile Iron Non-Pressure Utility Piping | 1.5.B.1.a |  | Certificates - Informational | Compliance Standards Certificates | Manufacturer and applicator of linings and coatings certificates | Construction
33 05 33.13 | Ductile Iron Non-Pressure Utility Piping | 1.5.B.4.a |  | Source Quality Control - Informational | Ductile Iron Pipe and Appurtenances Source Quality Control Reports | Test procedures for linings and Coatings in Pipe and Fittings. When requested by Engineer submit results of specified shop tests for pipe, fittings, linings, and coatings. | Construction
33 05 34.13 | Concrete Non-Pressure Utility Piping | 1.5.A.1.a |  | Product Data - Action | Concrete Non-Pressure Utility Pipe Product Data | Detailed data on piping, fittings, gaskets, fastening hardware and appurtenances, detailed description for maintenance, results from quality control test. Required Calculations. | Construction
33 05 34.13 | Concrete Non-Pressure Utility Piping | 1.5.B.1.a |  | Certificates - Informational | Manufacturer's Certificates of Conformance to Referenced Standards | Certification that each products conform to applicable reference standards | Construction
33 05 34.13 | Concrete Non-Pressure Utility Piping | 1.5.B.3.a |  | Manufacturers Instructions - Informational | Supplier Instructions | Submit instructions for handling, storing, and installing products. | Construction
33 05 34.13 | Concrete Non-Pressure Utility Piping | 1.5.B.4.a |  | Source Quality Control - Informational | Manufacturer's Source Quality Control Test | Submit manufactures’ Certificates for joint testing compliance in accordance with this Section and ASTM C497. | Construction
33 05 34.15 | Concrete Pressure Utility Piping | 1.5.A.1.a |  | Product Data - Action | Concrete Pressure Utility Pipe - Product Data | Detailed data on piping, fittings, gaskets, fastening hardware and appurtenances, detailed description for maintenance, results from quality control test. Required Calculations. | Construction
33 05 34.15 | Concrete Pressure Utility Piping | 1.5.A.2.a |  | Shop Drawings - Action | Concrete Pressure Utility Piping - Shop Drawings | Detailed drawings and data on piping and appurtenances | Construction
33 05 34.15 | Concrete Pressure Utility Piping | 1.5.B.1.a |  | Certificates - Informational | Manufacturer's Certificates of Conformance to Referenced Standards | Submit manufacturer's Certificates of compliance and suppliers instructions for handling, storing and installation products | Construction
33 05 34.15 | Concrete Pressure Utility Piping | 1.5.B.3.a |  | Manufacturers Instructions - Informational | Supplier Instructions | Suppliers instructions for handling, storing and installation products | Construction
33 05 37.13 | PVC Non-Pressure Utility Piping | 1.5.A.1.a |  | Product Data - Action | PVC Non-Pressure Utility Piping - Product Data | Submit product data on pipe, fittings, gaskets, hardware and appurtenances for compliance with Contract Documents | Construction
33 05 37.13 | PVC Non-Pressure Utility Piping | 1.5.B.1.a |  | Certificates - Informational | Compliance Standards Certificates | Submit manufacturer's Certificates of compliance | Construction
33 05 37.13 | PVC Non-Pressure Utility Piping | 1.5.B.4.a |  | Source Quality Control - Informational | Site Quality Control Reports | When requested by Engineer, submit results of source quality control tests. Ensure the quality control tests were completed on the same material installed. | Construction
33 05 37.13 | PVC Non-Pressure Utility Piping | 1.5.B.6.a |  | Qualifications Statements - Informational | Manufacturer's Qualifications | Qualifications of manufacturer and installer | Construction
33 05 37.16 | PVC Pressure Utility Piping | 1.5.A.1.a |  | Product Data - Action | PVC Pressure Utility Piping - Product Data | Product data on pipe, fittings, gaskets, hardware and appurtenances for compliance with Contract Documents | Construction
33 05 37.16 | PVC Pressure Utility Piping | 1.5.B.1.a |  | Certificates - Informational | Compliance to Standards Certificates | Manufacturer's Certificates of compliance | Construction
33 05 37.16 | PVC Pressure Utility Piping | 1.5.B.4.a |  | Source Quality Control - Informational | Site Quality Control Reports | When requested by Engineer, submit results of source quality control tests. Ensure the quality control tests were completed on the same material installed. | Construction
33 05 37.16 | PVC Pressure Utility Piping | 1.5.B.6.a |  | Qualifications Statements - Informational | Manufacturer's Qualifications | Qualifications of manufacturer and installer | Construction
33 05 38.13 | HDPE Non-Pressure Utility Piping | 1.5.A.1.a |  | Product Data - Action | HDPE Non-Pressure Utility Piping - Product Data | Product data on pipe, fittings, gaskets, hardware, pipe gasket lubricant and appurtenances sufficient to demonstrate compliance with the Contract Documents. | Construction
33 05 38.13 | HDPE Non-Pressure Utility Piping | 1.5.B.1.a |  | Certificates - Informational | Compliance Standards Certificates | Submit manufacturer's Certificates of compliance | Construction
33 05 38.13 | HDPE Non-Pressure Utility Piping | 1.5.B.4.a |  | Source Quality Control - Informational | Source Quality Control Reports | When requested by Engineer, submit results of source quality control tests. Ensure the quality control tests were completed on the same material installed. | Construction
33 05 38.13 | HDPE Non-Pressure Utility Piping | 1.5.B.6.a |  | Qualifications Statements - Informational | Manufacturer's Qualifications | Qualifications of manufacturer and installer | Construction
33 05 38.16 | HDPE Pressure Utility Piping | 1.5.A.1.a |  | Product Data - Action | HDPE Pressure Utility Piping- Product Data | Product data on pipe, fittings, gaskets, hardware, and appurtenances sufficient to demonstrate compliance with the Contract Documents. | Construction
33 05 38.16 | HDPE Pressure Utility Piping | 1.5.B.1.a |  | Certificates - Informational | Compliance Standards Certificates | Submit manufacturer's Certificates of compliance, submit contractor's Certificates of fusion, electrofusion operators training, and experience per Paragraph 1.4A, submit fusion EF parameter, test reports | Construction
33 05 38.16 | HDPE Pressure Utility Piping | 1.5.B.4.a |  | Source Quality Control - Informational | Source Quality Control Reports | When requested by Engineer, submit results of source quality control tests. Ensure the quality control tests were completed on the same material installed. | Construction
33 05 38.16 | HDPE Pressure Utility Piping | 1.5.B.5.a.1 |  | Field Quality Control - Informational | Notice of Initial Fusion | 48 hours prior to initial butt fusion joint provide Owner notice of work. | Construction
33 05 38.16 | HDPE Pressure Utility Piping | 1.5.B.5.b.1 |  | Field Quality Control - Informational | Data Logger Vault | Pressure test results and fusion logs from all butt fusions performed should be submitted to the Data Logger Vault daily. | Construction
33 05 38.16 | HDPE Pressure Utility Piping | 1.5.B.5.b.2 |  | Field Quality Control - Informational | Data Logger Vault | Pictures from all butt fusions performed should be submitted to the Data Logger Vault daily. | Construction
33 05 38.16 | HDPE Pressure Utility Piping | 1.5.B.5.b.3 |  | Field Quality Control - Informational | Data Logger Vault | Complete Data Logger Vault including pressure tests and fusion logs should be submitted as a close out submittal prior to substantial completion. | Construction
33 05 38.16 | HDPE Pressure Utility Piping | 1.5.B.5.b.4 |  | Field Quality Control - Informational | Data Logger Vault | Datalogger annual calibration and software version. | Construction
33 05 38.16 | HDPE Pressure Utility Piping | 1.5.B.6.a |  | Qualifications Statements - Informational | Generic Electrofusion Operator Training Test | Submit completed test from Appendix C of Municipal Advisor Board | Construction
33 05 38.16 | HDPE Pressure Utility Piping | 1.5.B.6.b |  | Qualifications Statements - Informational | Manufacturer's Qualifications | Qualifications of manufacturer and installer when requested by Engineer | Construction
33 05 38.16 | HDPE Pressure Utility Piping | 1.5.C.2.a |  | Record Documentation - Closeout | Fusion Installation Metrics | Data requested from Contractor and/or fusion provider to the Owner, approved data logger reports; fusion joint documentation data; as recorded information | Closeout
33 05 39 | FRP Non-Pressure Utility Piping | 1.5.A.1.a |  | Product Data - Action | FRP Non-Pressure Utility piping Product Data | Submit product data on pipe, fittings, gaskets, hardware and appurtenances | Construction
33 05 39 | FRP Non-Pressure Utility Piping | 1.5.B.1.a |  | Certificates - Informational | Compliance Standards Certificates | Submit manufacturer's Certificates of compliance | Construction
33 05 39 | FRP Non-Pressure Utility Piping | 1.5.B.3.a |  | Manufacturers Instructions - Informational | Manufacturer's Installation Instructions | Recommendations for installation of pipe | Construction
33 05 39 | FRP Non-Pressure Utility Piping | 1.5.B.4.a |  | Source Quality Control - Informational | Source Quality Control Reports | When requested by Engineer, submit results of source quality control tests. | Construction
33 05 39 | FRP Non-Pressure Utility Piping | 1.5.B.6.a |  | Qualifications Statements - Informational | Manufacturer's Qualifications | Qualifications of manufacturer and installer | Construction
33 05 41 | CMP Non-Pressure Utility Piping | 1.5.A.1.a |  | Product Data - Action | CMP Non-Pressure Utility Piping - Product Data | Product data on pipe, fittings, gaskets, hardware, pipe gasket lubricant and appurtenances sufficient to demonstrate compliance with the Contract Documents. | Construction
33 05 41 | CMP Non-Pressure Utility Piping | 1.5.B.1.a |  | Certificates - Informational | Compliance Standards Certificates | Submit manufacturer's Certificates of compliance | Construction
33 05 41 | CMP Non-Pressure Utility Piping | 1.5.B.4.a |  | Source Quality Control - Informational | Source Quality Control Reports | When requested by Engineer, submit results of source quality control tests. Ensure the quality control tests were completed on the same material installed. | Construction
33 05 41 | CMP Non-Pressure Utility Piping | 1.5.B.6.a |  | Qualifications Statements - Informational | Manufacturer's Qualifications | Qualifications of manufacturer and installer | Construction
33 05 51 | PP Non-Pressure Utility Piping | 1.5.A.1.a |  | Product Data - Action | PP Non-Pressure Utility Piping - Product Data | Product data on pipe, fittings, gaskets, hardware, pipe gasket lubricant and appurtenances sufficient to demonstrate compliance with the Contract Documents. | Construction
33 05 51 | PP Non-Pressure Utility Piping | 1.5.B.1.a |  | Certificates - Informational | Compliance with Standards Certificates | Submit manufacturer's Certificates of compliance | Construction
33 05 51 | PP Non-Pressure Utility Piping | 1.5.B.4.a |  | Source Quality Control - Informational | Source Quality Control Reports | When requested by Engineer, submit results of source quality control tests. Ensure the quality control tests were completed on the same material installed. | Construction
33 05 51 | PP Non-Pressure Utility Piping | 1.5.B.6.a |  | Qualifications Statements - Informational | Manufacturer's Qualifications | Qualifications of manufacturer and installer | Construction
33 11 00 | Water Piping Installation | 1.5.A.1.a |  | Product Data - Action | Manufacturer's Technical Information | Manufacturer’s literature and Specifications, as applicable, for products specified in this Section. | Construction
33 11 00 | Water Piping Installation | 1.5.A.1.b |  | Product Data - Action | Chlorine Product Data | Submit for chlorine for use in disinfection of watermains | Construction
33 11 00 | Water Piping Installation | 1.5.A.2.a |  | Shop Drawings - Action | Concrete Piping Laying Schedules | Concrete piping laying schedules | Construction
33 11 00 | Water Piping Installation | 1.5.A.2.b |  | Shop Drawings - Action | Water Piping Installation Details | Details of piping, specials, joints, harnessing and thrust blocks, and connections to piping, structures, equipment, and appurtenances. | Construction
33 11 00 | Water Piping Installation | 1.5.B.1.a |  | Certificates - Informational | Compliance Standards Certificates | Submit manufacturer's Certificates of compliance | Construction
33 11 00 | Water Piping Installation | 1.5.B.2.a |  | Test and Evaluation Reports - Informational | Testing Procedures | Testing procedures, methods, apparatus and sequencing. Engineer's approval prior to testing | Construction
33 11 00 | Water Piping Installation | 1.5.B.5.a |  | Field Quality Control - Informational | Water piping Installation Field Quality Control | Results of each specified Field Quality Control testing | Construction
33 11 00 | Water Piping Installation | 1.5.C.2.a |  | Record Documentation - Closeout | Water Piping Installation Record Documentation | Maintain accurate up-to-date record documents and piping elev. showing mods in the field with approved submittals relative to piping work. Include profile drawings | Closeout
33 12 00 | Water Appurtenances | 1.5.A.1.a |  | Product Data - Action | Water Appurtenances - Product Data | Submit product data sheet and complete catalog information for each type and size of fire hydrant. | Construction
33 12 00 | Water Appurtenances | 1.5.B.1.a |  | Certificates - Informational | Compliance Standards Certificates | Submit manufacturer's Certificates of compliance | Construction
33 31 00 | Sanitary Sewer Piping Installation | 1.5.B.5.a |  | Field Quality Control - Informational | Sanitary Sewer Piping Installation - Field Quality Control | Results of each specified Field Quality Control testing | Construction
33 32 19 | Public Utility Wastewater Pumping Stations | 1.5.A.1.a |  | Product Data - Action | Wastewater Pumping Stations - Product Data | Plug and Check Valve - Product Data | Construction
33 32 19 | Public Utility Wastewater Pumping Stations | 1.5.A.2.a |  | Shop Drawings - Action | Wastewater Pumping Stations Shop Drawings | Pump Outline Drawing, Station Drawing for Accessories, Electrical requirements for equipment, drawing, interior/exterior layouts of control panels, information on all pilot, and Plug and Check Valve - Shop Drawings | Construction
33 32 19 | Public Utility Wastewater Pumping Stations | 1.5.B.1.a |  | Certificates - Informational | Compliance Standards Certificates | Submit manufacturer's Certificates of compliance | Construction
33 32 19 | Public Utility Wastewater Pumping Stations | 1.5.B.3.a |  | Manufacturers Instructions - Informational | Manufacturer's Installation Instructions | Provide manufacturer’s’ recommended pump and appurtenances installation instructions. | Construction
33 32 19 | Public Utility Wastewater Pumping Stations | 1.5.B.4.a |  | Source Quality Control - Informational | Pump Performance Data and Physical Characteristics. | Drawings with performance data and physical characteristics. Certified performance results for each pump supplied | Construction
33 32 19 | Public Utility Wastewater Pumping Stations | 1.5.B.5.a |  | Field Quality Control - Informational | Field Quality Control Test Reports | Certified copies of test results | Construction
33 32 19 | Public Utility Wastewater Pumping Stations | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Manufacturer's Operation and Maintenance Material and Manuals | Manufacturer's O&M material and manuals for pumps and valves. | Closeout
33 32 19 | Public Utility Wastewater Pumping Stations | 1.5.C.4.a |  | Warranty Documentation - Closeout | Pump Warranty Information | Provide Warranty Information as specified within section. | Closeout
33 39 13 | Sanitary Utility Sewerage Manholes | 1.5.A.2.a |  | Shop Drawings - Action | Sanitary Utility Sewage Manholes - Shop Drawings | Manufacturers' shop drawings showing design and construction details for any special structures | Construction
33 39 13 | Sanitary Utility Sewerage Manholes | 1.5.A.2.b |  | Shop Drawings - Action | Special Structures - Shop Drawings | Shop drawings showing design and construction details for types of sanitary utility sewage manholes | Construction
33 41 00 | Storm Utility Piping Installation | 1.5.B.5.a |  | Field Quality Control - Informational | Field Quality Control Reports | Results of each specified Field Quality Control test | Construction
33 44 13 | Drainage Structures | 1.5.A.2.a |  | Shop Drawings - Action | Drainage Structures - Shop Drawings | Submit manufacturer’s Shop Drawings showing design and construction of all drainage structures | Construction
33 46 16.19 | Pipe Underdrains | 1.5.A.1.a |  | Product Data - Action | Pipe Underdrains - Product Data | Product data on pipe, fittings, gaskets, hardware, pipe gasket lubricant and appurtenances sufficient to demonstrate compliance with the Contract Documents. | Construction
33 46 16.19 | Pipe Underdrains | 1.5.B.1.a |  | Certificates - Informational | Compliance with Standards Certificates | Submit manufacturer's Certificates of compliance | Construction
33 46 16.19 | Pipe Underdrains | 1.5.B.4.a |  | Source Quality Control - Informational | Source Quality Control Reports | When requested by Engineer, submit results of source quality control tests. Ensure the quality control tests were completed on the same batch of material, as installed. | Construction
33 46 16.19 | Pipe Underdrains | 1.5.B.6.a |  | Qualifications Statements - Informational | Manufacturer's Qualifications | Qualifications of manufacturer and installer | Construction
33 47 32 | Rain Garden Construction | 1.5.A.1.a |  | Product Data - Action | Rain Garden - Product Data | Submit product data on plants, amended soil, mulch, and rain garden appurtenances sufficient to demonstrate compliance with the Contract Documents. | Construction
33 47 32 | Rain Garden Construction | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Rain Garden - Maintenance Data | Include cutting and trimming methods, types of application, frequency and recommended coverage of fertilizer | Closeout
33 49 13 | Storm Drainage Manholes | 1.5.A.2.a |  | Shop Drawings - Action | Storm Drainage Manholes - Shop Drawings | Drawings showing design and construction details for storm drainage manholes and special structures | Construction
33 49 13 | Storm Drainage Manholes | 1.5.A.2.b |  | Shop Drawings - Action | Special Structures - Shop Drawings | Detailed drawings showing design and construction details for any special structures | Construction
Division 40 - Process Interconnections
40 05 06 | Couplings, Adapters and Specials for Process Piping | 1.5.A.1.a |  | Product Data - Action | Manufacturer's Technical Information | Product data on each type of coupling, expansion joint, and other piping specialties and accessories, including gaskets, hardware, and appurtenances sufficient to demonstrate compliance with the Contract Documents. | Construction
40 05 06 | Couplings, Adapters and Specials for Process Piping | 1.5.A.2.a |  | Shop Drawings - Action | Piping Layout | Detailed drawings and data on piping and appurtenances | Construction
40 05 06 | Couplings, Adapters and Specials for Process Piping | 1.5.B.1.a |  | Certificates - Informational | Compliance with Standards Certificates | Submit manufacturer's Certificates of compliance | Construction
40 05 06 | Couplings, Adapters and Specials for Process Piping | 1.5.B.3.a |  | Manufacturers Instructions - Informational | Manufacturers' Instructions | Instructions for handling , storing, installing and adjusting products | Construction
40 05 06 | Couplings, Adapters and Specials for Process Piping | 1.5.B.4.a |  | Source Quality Control - Informational | Source Quality Control Reports | When requested by Engineer, submit results of source quality control tests. | Construction
40 05 06 | Couplings, Adapters and Specials for Process Piping | 1.5.B.6.a |  | Qualifications Statements - Informational | Manufacturer's Qualifications | Qualifications of manufacturer and installer | Construction
40 61 13 | Process Control Systems General Provisions | 1.5.A.1.a |  | Product Data - Action | Field Instruments Product Data | Detailed product data including product name, model number, data sheets, tag number, construction features, performance and operation data, installation details, mounting details, calibration details, service requirements, dimensions, and range of each device | Construction
40 61 13 | Process Control Systems General Provisions | 1.5.A.2.a |  | Shop Drawings - Action | Preliminary Control Panel Layout Shop Drawings | Preliminary Control Panel Layout Shop Drawings | Construction
40 61 13 | Process Control Systems General Provisions | 1.5.A.2.b |  | Shop Drawings - Action | Panels, Consoles, and Cabinets Shop Drawings | Layout drawings | Construction
40 61 13 | Process Control Systems General Provisions | 1.5.B.2.a |  | Test and Evaluation Reports - Informational | Control Panel Testing Startup Submittal | Red line shop drawings with contractor markups during installation | Construction
40 61 13 | Process Control Systems General Provisions | 1.5.B.4.a |  | Source Quality Control - Informational | Factory Acceptance Test | Description of testing procedures and result of test | Construction
40 61 13 | Process Control Systems General Provisions | 1.5.B.5.a |  | Field Quality Control - Informational | Field Quality Control Test Results | Completed field testing and calibration reports | Construction
40 61 13 | Process Control Systems General Provisions | 1.5.C.2.a |  | Record Documentation - Closeout | As-Builts / Final Completion | For each control panel (including PLC, pump protection, control station, etc.) that is modified or designed for the Project. | Closeout
40 61 93 | Process Control System - Input Output List | 1.5.A.2.a |  | Shop Drawings - Action | I/O Attribute Modifications | For each I/O attribute listed in the I/O list that cannot be used exactly as listed, submit an explanation of the reason for the deviation and propose a method to modify the I/O list information. Do not proceed with any configuration until a method of resolving deviations is accepted by the ENGINEER. | Construction
40 64 00 | Programmable Logic Controllers |  |  | Upon Request | Upon Request
40 67 03 | Control System Equipment Panel Construction | 1.5.A.1.a |  | Product Data - Action | Control Panel - Product Data | All component product data as specified in 40 61 13 Process Control System General Provisions. | Construction
40 67 03 | Control System Equipment Panel Construction | 1.5.A.2.a |  | Shop Drawings - Action | Control Panel - Shop Drawings | Electrical, instrumentation, and control drawings complete with control panel bill of materials. Included are the point-to-point wiring for field devices interfacing with systems control. Hard-wired field devices shall be included. | Construction
40 67 06 | Misc. Control Panel Devices | 1.5.A.1.a |  | Product Data - Action | Miscellaneous Control Panel - Product Data | All component product data as specified in 40 61 13 Process Control System General Provisions. | Construction
40 67 06 | Misc. Control Panel Devices | 1.5.A.2.a |  | Shop Drawings - Action | Miscellaneous Control Panel - Shop Drawings | Submit Product Data and Shop Drawings in one complete submittal package for this section | Construction
40 7x xx | Template for Instrumentation | 1.5.A.1.a |  | Product Data - Action | Manufacturer's Technical Information | Catalog cuts and product specifications for instrumentation specified. | Construction
40 7x xx | Template for Instrumentation | 1.5.A.2.a |  | Shop Drawings - Action | Instrumentation Shop Drawings | Installation and assembly drawings and specifically prepared data for instrumentation specified. | Construction
40 7x xx | Template for Instrumentation | 1.5.C.1.a |  | Operation and Maintenance Data - Closeout | Operation and Maintenance Data for Instrumentations | Operating instructions and maintenance data for materials and products for inclusion in O&M Manual. | Closeout