## Slide 1
Submittal Updates
September 26th 2019

## Slide 2: Background
10+ years ago, process started with Arcadis Master Specifications being modified to fit Fort Wayne’s needs
Master Specification were based off Master Format 2004 (MF04) and Construction Specification Institute (CSI)
2014 – Created Master Electrical Specifications
2015 – Created Master Instrumentation and Communications Specifications
Other Master Specifications added along the way
Now almost 100 City of Fort Wayne Master Specifications exist

## Slide 3: Other Master Documents Updates
EJCDC Division 00 / 01 update rollout to happen soon
Update from EJCDC 2002 Front End Documents to EJCDC 2018 Front End Documents
Update of Division 01 Master Specifications

## Slide 4: Order of Presentation
PART I Specification Format / Submittal Listing
Updating Submittal Section within Specifications
Updating Submittal Listing
PART II Submittal Types
Introduction of new transmittal templates associated with Action, Informational, Maintenance Materials, and Closeout Submittals
PART III Construction Administration
Modifications to Submittal Review Process

## Slide 5: Why?
Increase Organization of Submittals moving forward aligned with EJCDC and CSI Format
Coordination with PMIS to allow for searching of submittals
Coordination with PMIS coordinators for Project Submittal Listings
A standard and consistent submittal format
Introduction of new transmittal templates associated with Action, Informational, Maintenance Materials, and Closeout Submittals

## Slide 6: What we did?
Updated master specifications to reflect the changes to the submittal section
Created a General Information Bulletin (GIB) for Submittal Procedures
Created a Master Submittal Listing
Coordinated with the PMIS team to start usability within the system
Created new transmittal templates (Submittal Reply Form) associated with Action, Informational, Maintenance of Materials, and Closeout Submittals

## Slide 7: PART 1
Submittal Section Format
Specification Updating
Submittal Listing

## Slide 8: Submittal Types
Action
    Product Data
    Shop Drawings
    Samples
    Delegated Design (Rarely used)
Informational
    Quality Control
    Test Reports
    Qualifications
Maintenance of Material
    Spare Parts
Closeout
    O&M
    Record Documentation

## Slide 9: What was changed within the Submittal Section?
No updates to Submittals required in previous Master Specifications
Clear notation of Action, Informational, Maintenance Materials, and Closeout Submittals
Consistent formatting of each specification
Submittals will always have an Article Heading of 1.5 with consistent paragraphs and subparagraphs below

## Slide 12: How to edit project specifications
Non-Master Specifications – Start with Submittals Section Template (previous slide)
Coordinate early with Design Team (Consultants)
Never delete the article headings “A. Action Submittals”, “B. Informational Submittals”, “C. Closeout Submittals”, and “D. Maintenance Materials”
    Instead add “(NOT USED)”
The order of the subparagraphs, numbering, or labeling shouldn’t be changed since this is what creates the consistency within PMIS
Since everything is following a general format, editing must be done carefully to ensure the format isn’t changed from the standard

## Slide 14: Example: Action Submittal Required (Product Data)

## Slide 16: Example: Add an Action Submittal (Testing)

## Slide 18: Example: No Action Submittals

## Slide 19: Tutorial
New Submittal
Add Testing Submittal
Additional Product Data

## Slide 20: Submittal Listing
Called out in Specification 01 33 00 Submittal Procedures
Master Submittal Listing created for all Master Specification
Should be the start of the Submittal Listing for all projects
Stored within the existing Master Specification Folder (excel file)
Should be submitted no later than 95% design to allow for review and coordination with the Construction Management Team

## Slide 21
When new submittals and specifications are added the description box should be filled out for clarity.
  Description box should be consistent with what is written in the specifications.
The boxes are important for PMIS and Construction Administrator and should be filled out.
Submittal Listing

## Slide 22: Tutorial
Submittal Listing Tutorial

## Slide 23: PART II
Submittal Types
New Transmittal Reply Forms

## Slide 24: Submittal Types
Action
    Product Data
    Shop Drawings
    Samples
    Delegated Design (Rarely used)
Informational
    Quality Control
    Test Reports
    Qualifications
Maintenance of Material
    Spare Parts
Closeout
    O&M
    Record Documentation

## Slide 25: Why?
In accordance with EJCDC and CSI Format
Legal implications

## Slide 26: Submittal Responses
Action
    Approved
    Approved as Noted
    Approved as Noted – Resubmit
    Revise and Resubmit
    Not Approved
Action
    Approved – Contractor submitted exact product data as specified (No Comments)
    Approved as Noted – Contractor submitted exact product data as specified but wrong color (Fire Hydrant shall be yellow not blue)
    Approved as Noted – Resubmit – Contractor submitted shop drawings with easily understood changes and comments, but a clean copy is desired for Record Keeping (Reviewer does not want to hold up Project for another round of submittals)
    Revise and Resubmit– Contractor submitted right product but wrong size (Pipe shall be 12” and not 18”)
    Not Approved– Contractor submitted wrong product (Gate Valve vs. Ball Valve)

## Slide 27: Submittal Responses
All Informational, Maintenance Material, and Closeout Submittals that do not indicate compliance with the Contract Documents are to result in the Engineer’s written disposition of “not accepted” and the reason(s) therefor.
Informational
    Accepted
    Not Accepted
Maintenance Material
    Accepted
    Not Accepted
Closeout
    Accepted
    Not Accepted

## Slide 28: Transmittal Reply Forms
Action Submittal Reply (Non-Delegated Design)

## Slide 30: Transmittal Reply Forms
Delegated Design Action Submittal Reply

## Slide 32: Transmittal Reply Forms
Informational / Closeout / Maintenance Materials Submittal Reply

## Slide 34: PART III
General
Construction Administration

## Slide 35: Who reviews and stamps the submittal?
Engineer’s design professional who prepared the Drawings and Specifications should be the person who reviews and stamps the associated submittals for the elements of the Work designed by that engineer. The in-house design professional can delegate the responsibility.
Construction Manager will review the submittal during the first review and should add comments in PMIS, but should not be stamping the submittals or adding comments after the Engineer stamps the submittal reply form
Construction Manager will not be able to edit after Engineer stamps, but should coordinate any additional comments with Engineer prior to final workflow completion
One Submittal Reply Form and one reviewer stamp

## Slide 36: Workflow Process Diagram
Contractor
CM Add Comments
PM
CM Final Check and Coordination.
No comments.
Consultant
(If used)
CM to coordinate with PM if
CM wants to clarify a comment
Workflow Completion

## Slide 37: Engineer’s Review Time
Do not specify in the Bidding Documents or the Contract Documents a maximum or “guaranteed” time for the Engineer’s review and responses to submittals.
Goal is 14 days

## Slide 38: Specifying Required Submittals
Substantial time by various entities participating in a construction project is required for preparing, transmitting, reviewing, filing, and using submittals.
Specifier should review and understand the need for each submittal required in the Specifications
Specifications were set up with the easier to delete than add mentality
Don’t assume, go ask!

## Slide 39: Submittals Not Required
Submittals not required by the Contract Documents should be returned to the Contractor without review and should not be retained in the Engineer’s files or recorded in the Engineer’s submittal log.
Accepting and reviewing submittals not required has the potential to unnecessarily increase the Engineer’s liability.
Even when a submittal that is not required is accepted and saved “for record only”, there would very likely be an expectation by a court or arbitration board that the Engineer is obligated to review and comment on it.

## Slide 40: Website Files
Zip File of All Master Specifications
    No individual specifications
01 33 00 General Information Bulletin (GIB)
Presentation
Master Submittal Listing
Transmittal Reply Forms
  Action
  Action (Delegated Design)
  Informational / Maintenance Materials / Closeout

## Slide 41: Schedule
Files are available on the Website as of Sept. 26th
Update 01 33 00 Submittals Specification for new submittal responses since PMIS will be changing
  Add Approved as Noted – Resubmit
  Removed Hold Notice
Any New Project that has not started editing specifications should follow New Submittal Format

## Slide 42: Questions
?

## Slide 43: Delegated Design Applicability
Delegated Design Submittals should be used sparingly and with care.
If a delegated design is proposed for a project consult senior management to confirm applicability.
Delegated design should be for items that become part of the completed work.
Provide design criteria and performance standards
Submittals of temporary construction, such as excavation supports (including sheeting, shoring, bracing, and wales) designed by a design professional retained by the Contractor are typically not part of the completed, permanent Work and therefore may not be designed as “delegated design” submittals.

## Slide 44: Examples of Delegated Design
Digesters (steel).
Geodesic domes.
Tunnel lining systems.
Water storage tanks (steel or pre-stressed concrete).

## Slide 45: Reason for Delegated Design
The design complexity of certain components of the permanent work and the special expertise required for that design that is beyond the acumen and skill of DPRs.
In order to reduce the cost of the design and construction of the permanent work.
Increasing prevalence of single-source site-erected/assembled systems consisting of equipment, components and interconnections.
Increasing emphasis on constructability considerations in connection with the design of permanent work.